## Sheet1
Royal Borough of Kensington and Chelsea Works and Events Bulletin - 16th October 2025
Works Originator | Road | Location | Effect | From Date | To Date | Time | Reason | Comment | Council Ward | Line Number
|  |  |  | RBKC Footway Work | [5 empty] | 3
Royal Borough of Kensington and Chelsea | South Edwardes Square | Both sides and Edwards Square(NFW) | Footway Closed with local diversion | 2025-09-01 | 2025-11-12 | From 8.00am to 5.00pm | Footway improvement works |  | Abingdon | 4
Royal Borough of Kensington and Chelsea | Highlever Road | 154-148 , (Remaining FW) | Footway Closed with local diversion | 2025-09-01 | 2025-12-15 | From 8.00am to 5.00pm | Footway improvement works |  | Dalgarno | 5
Royal Borough of Kensington and Chelsea | South Edwardes Square | Both sides and Edwards Square(NFW) |  | 2025-09-01 | 2025-11-12 | From 8.00am to 5.00pm | Footway improvement works |  | ABINGDON | 6
Royal Borough of Kensington and Chelsea | Oakley Street | o/s 3 and o/s 104 to King's Road | Footway Closed with local diversion and Temporary Traffic Lights | 2025-09-15 | 2025-10-31 | From 8.00am to 5.00pm | Footway improvement works |  | Various Wards | 7
Royal Borough of Kensington and Chelsea | King's Road | outside 183, Outside IV Res - Oakly Street |  | 2025-09-15 | 2025-10-28 | From 8.00am to 5.00pm | Footway improvement works |  | Royal Hospital | 8
Royal Borough of Kensington and Chelsea | Sirdar Road | Treadgold - 27 Wilsham Street | Footway Closed with local diversion | 2025-09-22 | 2026-02-03 | From 8.00am to 5.00pm | Footway improvement works |  | Notting Dale | 9
Royal Borough of Kensington and Chelsea | Cadogan Square | Opposite 3 to 13 and from lamp post 002 to Pont Street (WFW) and opposite 71-72 (NFW |  | 2025-09-29 | 2026-02-12 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 10
Royal Borough of Kensington and Chelsea | Denbigh Road | Denbigh Terrace to Westbourne Grove (EFW) and 5 to Westbourne Grove (WFW) | Footway Closed with local diversion | 2025-09-30 | 2025-10-28 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 11
Royal Borough of Kensington and Chelsea | Denbigh Road | Denbigh Terrace to Westbourne Grove (EFW) and 5 to Westbourne Grove (WFW) |  | 2025-09-30 | 2025-10-28 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 12
Royal Borough of Kensington and Chelsea | Dawson Place | Pembridge Place to Chepstow Place (NFW) |  | 2025-10-13 | 2025-11-05 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 13
Royal Borough of Kensington and Chelsea | Cheyne Walk | Cheyne Mews to Royal Hospital Road (NFW) |  | 2025-10-13 | 2025-12-17 | From 8.00am to 5.00pm | Footway improvement works |  | Royal Hospital | 14
Royal Borough of Kensington and Chelsea | St Lawrence Terrace | Chesterton Road junction to no.18 (EFW) and (WFW) at end of no. 38 Oxford Gardens to end of no. 21 | Footway Closed with local diversion | 2025-10-13 | 2025-11-27 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 15
Royal Borough of Kensington and Chelsea | Tavistock Crescent | Tavistock Road to 24 Tavistock Crescent (WFW) | Footway Closed with local diversion | 2025-10-16 | 2025-11-10 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 16
Royal Borough of Kensington and Chelsea | Tavistock Crescent | Tavistock Road to 24 Tavistock Crescent (WFW) |  | 2025-10-16 | 2025-11-10 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 17
Royal Borough of Kensington and Chelsea | Cadogan Place | Opposite 31-47 and 58 to Cadogan Place (WFW) |  | 2025-10-20 | 2025-12-04 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 18
Royal Borough of Kensington and Chelsea | Chesterton Road | St Lawrence Terrace to Portobello Road (both sides) | Footway Closed with local diversion | 2025-10-29 | 2025-12-16 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 19
Royal Borough of Kensington and Chelsea | Oxford Gardens | Opposite 21-29 and 7-11 to street lamp 002 (NFW) | Footway Closed with local diversion | 2025-11-04 | 2025-11-20 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 20
Royal Borough of Kensington and Chelsea | Southwell Gardens | From Grenville Place to the Church gate (SFW) |  | 2025-11-04 | 2025-11-27 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 21
Royal Borough of Kensington and Chelsea | Ladbroke Gardens | From 35 to 21 Stanley Gardens (SFW) | Footway Closed with local diversion | 2025-11-05 | 2025-11-19 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 22
Royal Borough of Kensington and Chelsea | Colville Gardens | Colville Terrace to Talbot Road (EFW) | Footway Closed with local diversion | 2025-11-11 | 2025-12-03 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 23
Royal Borough of Kensington and Chelsea | Pont Street | Outside 31-39 and road side footway between Cadogan Square and Cadogan Square (SFW) |  | 2025-11-11 | 2025-12-08 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 24
Royal Borough of Kensington and Chelsea | Pelham Crescent | Pelham Place to Fulham Road | Footway Closed with local diversion | 2025-11-13 | 2025-12-11 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 25
Royal Borough of Kensington and Chelsea | Jameson Street | Kensington Place to Uxbridge Street (WFW) | Footway Closed with local diversion | 2025-11-20 | 2025-12-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 26
Royal Borough of Kensington and Chelsea | Jameson Street | Kensington Place to Uxbridge Street (WFW) |  | 2025-11-20 | 2025-12-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 27
Royal Borough of Kensington and Chelsea | Smith Street | 1 to 10 ( incl. 1-7 Durham Place) (SFW) |  | 2025-11-28 | 2025-12-15 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 28
Royal Borough of Kensington and Chelsea | Colville Terrace | Colville Gardens to Powis Square (NFW) | Footway Closed with local diversion | 2025-12-04 | 2025-12-15 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 29
Royal Borough of Kensington and Chelsea | Ladbroke Road | Ladbroke Terrace to Kensington Park Road (NFW) | Footway Closed with local diversion | 2026-01-05 | 2026-02-26 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 30
Royal Borough of Kensington and Chelsea | Victoria Road | End to St Alban's Grove - (EFW) |  | 2026-01-05 | 2026-02-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 31
Royal Borough of Kensington and Chelsea | Doyley Place | Outside Wilbraham House to Mansion House (EFW) |  | 2026-01-05 | 2026-02-06 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 32
Royal Borough of Kensington and Chelsea | Hillsleigh Road | Aubrey Walk to Campden Hill Square (WFW) and outside 16-17 (EFW) | Footway Closed with local diversion | 2026-01-06 | 2026-02-20 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 33
Royal Borough of Kensington and Chelsea | Aubrey Walk | Outside 14 to Hillsleigh Road (NFW) | Footway Closed with local diversion | 2026-01-06 | 2026-02-20 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 34
Royal Borough of Kensington and Chelsea | Berkeley Gardens | Kensington Church Street (SFW) from no. 104 to no. 7 and (NFW) no. 106 to 21b Brunswick Gardens | Footway Closed with local diversion | 2026-01-06 | 2026-01-26 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 35
Royal Borough of Kensington and Chelsea | Norland Road | 22-24 Norland Road/ Shepherds Bush underpass |  | 2026-01-06 | 2026-03-02 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 36
Royal Borough of Kensington and Chelsea | Ladbroke Grove WFW | Cornwall Crescent to Lancaster Road | Footway Closed with local diversion | 2026-01-07 | 2026-03-03 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 37
Royal Borough of Kensington and Chelsea | Kensington Church St | Kensington Mall to Notting Hill Gate (EFW) | Footway Closed with local diversion | 2026-01-07 | 2026-02-09 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 38
Royal Borough of Kensington and Chelsea | Kensington Ch Walk | Outside Macmillan House to end of paved surfacing at church |  | 2026-01-07 | 2026-03-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 39
Royal Borough of Kensington and Chelsea | Campden Hill Square | Opposite 24 to Holland Park Ave (WFW) and no.16 to Hillsleigh Road (SFW) | Footway Closed with local diversion | 2026-01-12 | 2026-02-12 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 40
Royal Borough of Kensington and Chelsea | Queens Gate | Cromwell Road to Queen's Gate Place (WFW) |  | 2026-01-12 | 2026-03-20 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 41
Royal Borough of Kensington and Chelsea | Morgan Road | Wornington Road to St Ervans Road (both sides) | Footway Closed with local diversion | 2026-01-26 | 2026-02-13 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 42
Royal Borough of Kensington and Chelsea | Morgan Road | Wornington Road to St Ervans Road (both sides) |  | 2026-01-26 | 2026-02-13 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 43
Royal Borough of Kensington and Chelsea | Brunswick Gardens | Outside 11 to 33 Berkely Gardens WFW + opposite to 3-7 (both sides) WFW | Footway Closed with local diversion | 2026-01-27 | 2026-02-18 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 44
Royal Borough of Kensington and Chelsea | Wilbraham Place | Outside 9/9a to D'Oyley Place(NFW) |  | 2026-02-09 | 2026-02-17 | From 8.00am to 5.00pm | Footway improvement works |  | Royal Hospital | 45
Royal Borough of Kensington and Chelsea | Notting Hill Gate | O/S 34 - Linden Gardens - NFW | Footway Closed with local diversion | 2026-02-10 | 2026-03-09 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 46
Royal Borough of Kensington and Chelsea | Aubrey Road | Outside 8c to Holland Park Road (WFW) and no. 29 to Holland Park Road (EFW) | Footway Closed with local diversion | 2026-02-13 | 2026-04-09 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 47
Royal Borough of Kensington and Chelsea | Elkstone Road | Between lamp posts 010 and 016 (NFW) |  | 2026-02-16 | 2026-03-19 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 48
Royal Borough of Kensington and Chelsea | Draycott Avenue | Outside Nell Gwynn House trade entrance SFW and NFW at Cadagon Street and opposite Mossop St (SFW) |  | 2026-02-18 | 2026-03-11 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 49
Royal Borough of Kensington and Chelsea | Campden Hill Gardens | Opposite no 15 to Campden Hill Road (WFW)Opposite no 15 to Campden Hill Road (WFW) | Footway Closed with local diversion | 2026-02-19 | 2026-03-12 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 50
Royal Borough of Kensington and Chelsea | Kensington Mall | Kensington Church Street to Palace Garden Terrace (SFW) | Footway Closed with local diversion | 2026-02-19 | 2026-02-27 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 51
Royal Borough of Kensington and Chelsea | Palace Gardens Terrace | Outside 82-102 and 60-64 - (EFW) | Footway Closed with local diversion | 2026-03-02 | 2026-03-25 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 52
Royal Borough of Kensington and Chelsea | Kensington Ch St | Holland Street to Holland Place (WFW) |  | 2026-03-02 | 2026-04-01 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 53
Royal Borough of Kensington and Chelsea | Gloucester Road | Kynance Place to Victoria Road (WFW) |  | 2026-03-03 | 2026-04-01 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 54
Royal Borough of Kensington and Chelsea | Westbourne Park Rd | Ladbroke Grove to opposite 338 - SFW | Footway Closed with local diversion | 2026-03-04 | 2026-03-16 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 55
Royal Borough of Kensington and Chelsea | Ladbroke Grove | Outside 2 to 4 (EFW) | Footway Closed with local diversion | 2026-03-10 | 2026-03-30 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 56
Royal Borough of Kensington and Chelsea | Ixworth Place | Opposite Pond Place to Marlborough Crescent and (SFW) and at Pond Place (NFW) |  | 2026-03-12 | 2026-03-19 | From 8.00am to 5.00pm | Footway improvement works |  | Stanley | 57
Royal Borough of Kensington and Chelsea | Upper Cheyne Row | Oakley Street to Cheyne Row (SFW) |  | 2026-03-17 | 2026-03-25 | From 8.00am to 5.00pm | Footway improvement works |  | Chelsea Riverside | 58
Royal Borough of Kensington and Chelsea | Fulham Road | Dovehouse Street to opposite Sumner Place (SFW) |  | 2026-03-23 | 2026-04-02 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 59
|  |  |  | RBKC WEEKDAY RESURFACING | [5 empty] | 60
Royal Borough of Kensington & Chelsea | Oxford Gardens | On the 4 Junctions with St Marks Rd | Multiway Signals | 2025-10-27 | 2025-11-07 | From 8.00am to 5.00pm | Sets removal in all 4 traffic ramps |  | St Helen's | 61
Royal Borough of Kensington and Chelsea | Dalgarno Way | Lamp 0014 to 0018 Sutton Way (corner) - Table Top | Road Closure | 2025-12-01 | 2025-12-01 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Dalgarno | 62
Royal Borough of Kensington and Chelsea | Dalgarno Way | Dalgarno Gardens to No.6 | Road Closure | 2025-12-01 | 2025-12-01 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Dalgarno | 63
Royal Borough of Kensington and Chelsea | Lansdowne Rise | Clarendon Road - Lansdown Crescent |  | 2025-12-02 | 2025-12-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 64
Royal Borough of Kensington and Chelsea | Lansdowne Road | Lansdowne Rise - St John Gardens |  | 2025-12-02 | 2025-12-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 65
Royal Borough of Kensington and Chelsea | St Johns Gardens | Clarendon Road - Ladbroke Grove | Road Closure | 2025-12-04 | 2025-12-05 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 66
Royal Borough of Kensington and Chelsea | Hillgate Place | Outside 73-77 to Jameson Street |  | 2026-01-12 | 2026-01-12 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 67
Royal Borough of Kensington and Chelsea | Denbigh Road | From 16 to Westbourne Grove | Road Closure | 2026-01-13 | 2026-01-13 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 68
Royal Borough of Kensington and Chelsea | All Saints Road | Tavistock Rd to Tavistock Crescent | Road Closure | 2026-01-14 | 2026-01-14 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 69
Royal Borough of Kensington and Chelsea | Tavistock Road | Junction at All Saint's Road | Road Closure | 2026-01-14 | 2026-01-14 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 70
Royal Borough of Kensington and Chelsea | Tavistock Crescent | All Saint's Road to St Luke's Road | Road Closure | 2026-01-14 | 2026-01-14 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 71
Royal Borough of Kensington and Chelsea | Farm Place | From Hillgate Place to Uxbridge Road |  | 2026-01-16 | 2026-01-16 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 72
Royal Borough of Kensington and Chelsea | Hornton Street | Holland Street to Gloucester Walk | Road Closure | 2026-01-26 | 2026-01-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 73
Royal Borough of Kensington and Chelsea | Holland Street | Campden Hill Road to Hornton Street | Road Closure | 2026-01-26 | 2026-01-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 74
Royal Borough of Kensington and Chelsea | Sloane Avenue | No. 22 to Draycott Place and Anderson Street | Road Closure | 2026-01-28 | 2026-01-28 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 75
Royal Borough of Kensington and Chelsea | Draycott Place | Between Sloane Avenue and O/S no. 57 | Road Closure | 2026-01-28 | 2026-01-28 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 76
Royal Borough of Kensington and Chelsea | D'Oyley Street | Lamp post 001 to Sloane Gate Mansion | Road Closure | 2026-01-28 | 2026-01-28 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 77
Royal Borough of Kensington and Chelsea | Ellis Street | From Sloane Street to 11/12 Ellis street | Road Closure | 2026-01-28 | 2026-01-28 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 78
Royal Borough of Kensington and Chelsea | Grenville Place | From No. 3 to Cornwall Gardens Junction | Road Closure | 2026-01-30 | 2026-01-30 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 79
Royal Borough of Kensington and Chelsea | Emperor's Gate | From Grenville Place to end of no. 6 | Road Closure | 2026-01-30 | 2026-01-30 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 80
Royal Borough of Kensington and Chelsea | Southwell Gardens | Grenville Place to no. 8 Southwell Gardens | Road Closure | 2026-01-30 | 2026-01-30 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 81
Royal Borough of Kensington and Chelsea | Sydney Street | Cale Street to Fulham Road | Road Closure | 2026-02-02 | 2026-02-02 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 82
Royal Borough of Kensington and Chelsea | Cale Street | Dovehouse Road to Sydney Street | Road Closure | 2026-02-03 | 2026-02-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 83
Royal Borough of Kensington and Chelsea | Holbein Place | Pimlico Road to Graham Terrace, Whittaker St to Sloane Gardens | Road Closure | 2026-02-04 | 2026-02-04 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 84
Royal Borough of Kensington and Chelsea | Cadogan Gate | Sloane Street to Cadogan Square | Road Closure | 2026-02-06 | 2026-02-06 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 85
Royal Borough of Kensington and Chelsea | Bedford Gardens | Campden Hill Road to Kensington - 4x humps | Road Closure | 2026-02-09 | 2026-02-11 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 86
Royal Borough of Kensington and Chelsea | Egerton Terrace | Egerton Place to Egerton Gardens | Road Closure | 2026-02-12 | 2026-02-13 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 87
Royal Borough of Kensington and Chelsea | Egerton Gardens | Egerton Crescent to Egerton Terrace | Road Closure | 2026-02-12 | 2026-02-13 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 88
Royal Borough of Kensington and Chelsea | St Leonards Terrace | Smith Street to Cheltenham Terrace | Road Closure | 2026-02-16 | 2026-02-18 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 89
Royal Borough of Kensington and Chelsea | Flood Street | Royal Hospital Road to no. 77 | Road Closure | 2026-02-19 | 2026-02-20 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Chelsea Riverside | 90
Royal Borough of Kensington and Chelsea | St Lawrence Terrace | Oxford Gardens to Chesterton Rd | Road Closure | 2026-02-23 | 2026-02-26 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Golborne | 91
Royal Borough of Kensington and Chelsea | Westbourne Grove | Denbigh Road to Ledbury Road | Road Closure | 2026-02-24 | 2026-02-24 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 92
Royal Borough of Kensington and Chelsea | Cadogan Gardens | Cadogan Gardens to Cadogan Gardens | Road Closure | 2026-02-25 | 2026-02-25 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 93
Royal Borough of Kensington and Chelsea | Cadogan Gardens | Cadogan Gardens to Cadogan Gardens | Road Closure | 2026-02-25 | 2026-02-25 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 94
Royal Borough of Kensington and Chelsea | Gloucester Road | o/s no. 110 to o/s 57 and o/s nos. 39/41 to no. 5 | Road Closure | 2026-02-26 | 2026-02-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 95
Royal Borough of Kensington and Chelsea | Pond Place | From end to Fulham Road | Road Closure | 2026-03-02 | 2026-03-02 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 96
Royal Borough of Kensington and Chelsea | Bury Walk | between nos. 43 to 49 | Road Closure | 2026-03-02 | 2026-03-02 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 97
Royal Borough of Kensington and Chelsea | Ladbroke Road | Horbury Crescent to Kensington Park Road | Road Closure | 2026-03-03 | 2026-03-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Pembridge | 98
Royal Borough of Kensington and Chelsea | Stanford Road | from end to St Alban's Grove | Road Closure | 2026-03-04 | 2026-03-04 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 99
|  |  |  | RBKC WEEKEND WORKS | [5 empty] | 100
101
|  |  |  | RBKC NIGHT RESURFACING | [5 empty] | 102
Royal Borough of Kensington and Chelsea | Cromwell Place | Old Brompton Road to Thurloe Place | Road Closure | 2026-02-05 | 2026-02-05 | From 8.00PM to 6.00AM | Carriageway Resurfacing | Nightworks | Brompton and Hans Town | 103
Royal Borough of Kensington and Chelsea | Sloane Square | Sloane Street to Lower Sloane Street | Road Closure | TBA | TBA | From 8.00PM to 6.00AM | Carriageway Resurfacing | Nightworks | Royal Hospital | 104
|  |  |  | RBKC DRAINAGE WORKS | [5 empty] | 105
Royal Borough of Kensington and Chelsea | Arundel Gardens | 48 | Road Closure | 14/10/25 | 17/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Colville | 106
Royal Borough of Kensington and Chelsea | Arundel Gardens | 48 | Road Closure | 14/10/25 | 17/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Colville | 107
Royal Borough of Kensington and Chelsea | Westbourne Grove | 236 | Road Closure | 20/10/25 | 24/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Colville | 108
Royal Borough of Kensington and Chelsea | Victoria Grove | 18 | Road Width Reduced | 21/10/25 | 23/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Queens Gate | 109
Royal Borough of Kensington and Chelsea | Millmans Street | 6 | Road Width Reduced | 22/10/25 | 26/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Chelsea Riverside | 110
Royal Borough of Kensington and Chelsea | Redfield Lane | 20 | Road Width Reduced | 24/10/25 | 29/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Earls Court | 111
Royal Borough of Kensington and Chelsea | Ledbury Road | 47 | Road Width Reduced | 24/10/25 | 30/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Colville | 112
Royal Borough of Kensington and Chelsea | Shawfield Street | 13 | Road Width Reduced | 28/10/25 | 31/10/25 | From 8.00 am to 5.00pm | Gully repair works |  | Royal Hospital | 113
Royal Borough of Kensington and Chelsea | Elvaston Mews | 25 | Road Width Reduced | 29/10/25 | 04/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | Queens Gate | 114
Royal Borough of Kensington and Chelsea | Kensington High Street | 207 | Lane Closure | 03/11/25 | 06/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | Abingdon | 115
Royal Borough of Kensington and Chelsea | Pimlico Road | Holbein House | Road Width Reduced | 04/11/25 | 07/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | Royal Hospital | 116
Royal Borough of Kensington and Chelsea | Kelfield Gardens | Kelfield Court | Road Width Reduced | 06/11/25 | 11/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | St Helens | 117
|  |  |  | RBKC SPECIAL ENGINEERING PROJECTS | [5 empty] | 118
Royal Borough of Kensington and Chelsea | Sloane Square | Junction with Symons Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 2025-03-31 | 2025-10-27 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 119
Royal Borough of Kensington and Chelsea | Symons Street | Cadogan Gardens to Sloane Square | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 2025-03-31 | 2025-10-27 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Compound Area | Royal Hospital | 120
Royal Borough of Kensington and Chelsea | Ensor Mews | Jnc Cranley Gardens | Road Closed with local diversion | 2025-08-27 | 2025-12-10 | Between 8.00am on first day until 6.00pm on final day. | Repair works to Archway |  | Courtfield | 121
Royal Borough of Kensington and Chelsea | Kensington Park Road | Between it's junctions with Elgin Crescent & Blenheim Crescent | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 29/09/25 | 16/06/26 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Coville | 122
Royal Borough of Kensington and Chelsea | Gloucester Road | Between its junctions with Stanhope Gardens, Courtfield Road & A4 Cromwell Road | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 03/11/25 | 10/07/26 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Courtfield | 123
Royal Borough of Kensington and Chelsea | Clarendon Road | At it's junctions with Dulford Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 2026-02-09 | 2026-03-13 | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Notting Dale | 124
Royal Borough of Kensington and Chelsea | Albert Bridge | Bridge Closure | Bridge Closed for maintenance works | 2026-07-20 | 2026-09-14 | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Bridge maintenance works | Chelsea Riverside | 125
Royal Borough of Kensington and Chelsea | Lower Sloane Street | Junction with Sloane Square | Southbound Directional Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | On Hold | On Hold | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 126
Royal Borough of Kensington and Chelsea | Lower Sloane Street | Junction with Sloane Square | Northbound Directional Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | On Hold | On Hold | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 127
Royal Borough of Kensington and Chelsea | Elm Park Gardens | At it's junctions with Elm Park Road and Fulham Road | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Tree islands) | Stanley | 128
Royal Borough of Kensington and Chelsea | Harrington Gardens | At it's junctions with Collingham Gardens | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Courtfield | 129
Royal Borough of Kensington and Chelsea | Ladbroke Square | At it's junctions with Ladbroke Terrace | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Speed Humps) | Pembridge | 130
Royal Borough of Kensington and Chelsea | Queen's Gate | At it's junctions with Elvaston Place / TBC | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Speed Humps) | Queen's Gate | 131
Royal Borough of Kensington and Chelsea | Sidar Road | At it's junctions with Mary Place and Wilsham Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Notting Dale | 132
Royal Borough of Kensington and Chelsea | Silchester Road | At it's junctions with Lancaster Road | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Carriageway) | Notting Dale | 133
Royal Borough of Kensington and Chelsea | St Quintins Avenue | At it's junctions with Pangbourne Avenue & Wallingford Avenue | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Dalgarno & St Helens | 134
|  |  |  | UTILITY COMPANY WORKS | [5 empty] | 135
M Group for Thames Water | Whitehead's Grove | Sloane Avenue to Draycott Avenue | Road Closed with local diversion | 29/08/25 to 05/09/25 | Backup Dates 23-31/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 136
Kelly Traffic Management for Virgin Media | Pembridge Road | Portobello Road to Kensington Park Road | Southbound Directional Road Closed with local diversion | 29/08/25 to 05/09/25 | Backup Dates 23-31/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Pembridge | 137
Thames Water | Addison Avenue | Jnc Holland Park Avenue | Road Closed with local diversion | 08-21/09/25 | Backup Dates 07-21/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Norland | 138
UK Power networks Limited | Malton Road | 2 to 4 | Road Closed with local diversion | 15-19/09/25 | Backup Dates 29/09/25 to 03/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | St Helen's | 139
Thames Water | Alexander Square | 17 | Road Closed with local diversion | 22-26/09/25 | Backup Dates 20-24/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 140
Cappagh for Thames Water | Mossop Street | 17 | Road Closed with local diversion | 2025-09-29 | 2025-10-17 | From 8.00am on first day until 6.00pm on final day | Utility works | Emergency Utility Works | Brompton and Hans Town | 141
Barhale for Thames Water | Pont Street | S/o Green Taxi Hut Jnc Cadogan Place | Lane Restrictions - Chicane | 2025-10-01 | 2025-12-02 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 142
OCU Group Limited | Kensington High Street | Junction of Allen Street | Prohibited Right hand turn with local diversion | 13-17/10/25 | Backup dates 20-24/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Abingdon | 143
Thames Water | Harrington Road | Junction of Glendower Place | Westbourne Directional Road Closure | 2025-10-16 | TBA | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 144
M Group for Thames Water | Sydney Street | Fulham Road to outside 16 | Road Closed with local diversion | 24/10/25 to 02/11/25 | Backup Dates 21-30/11/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Stanley | 145
M Group for Thames Water | Kensington Church Court | R/o 82 Kensington High Street | Road Closed with local diversion | 2025-10-27 | 2025-10-29 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 146
Thames Water | Blenheim Crescent | Jnc Kensington Park Road | Road Closed with local diversion | 27-29/10/25 | Backup Dates 03-05/11/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Colville | 147
Lanes Group PLC for Thames Water | Kenway Road | Whole Road | Road Closed with local diversion | 2025-10-27 | 2025-10-31 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Earl's Court | 148
Sunbelt Rentals for BT | Dalgarno Gardens | Barlby Road to Dalgarno Way | Road Closed with local diversion | 2025-10-30 | 2025-10-30 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Dalgarno | 149
Lanes Group PLC for Thames Water | Hogarth Road | Whole Road | Road Closed with local diversion | 2025-11-03 | 2025-11-05 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Earl's Court | 150
Keltic Traffic Management for Cadent Gas | Ifield Road | Jnc Fulham Road | Road Closed with local diversion | 2025-11-03 | 2025-11-07 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Redcliffe | 151
M Group for Thames Water | Mary Place | Walmer Road to Avondale Park Road | Road Closed with local diversion | 2025-11-03 | 2025-11-14 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Abingdon | 152
Barhale for Thames Water | Pont Street | Chesham Place | Multiway Signals | 2025-11-10 | 2025-11-20 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 153
OCU Group for BT | Kensington High Street | Hornton Street to Kensington Church Street | Eastbound Directional Road closed with local diversion | 2025-11-16 | Backup date 23/11/2025 | From 8.00am until 10.00pm | Utility works |  | Holland | 154
Thames Water | Launceston Place | 3 | Road Closed with local diversion | 18-19/11/25 | Backup Dates 24-25/11/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 155
Thames Water | Cadogan Square | 59 | Road Closed with local diversion | 20-21/11/25 | Backup Dates 23-24/11/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 156
Kelly Traffic Management for Virgin Media | Kensington Church Street | Dukes Lane to O/s 39 | Footway Closed with local diversion | 2025-11-24 | 2025-11-26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 157
M Group for Thames Water | Kensington High Street | Kensington Church Street | Prohibited Right Hand Turn with local diversion | 24-27/11/25 | Backup Dates 12-15/01/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 158
Vital Energi | Dulford Street | Clarendon Road to Walmer Street | Road Closed with local diversion | 2025-11-24 | 2026-02-09 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Notting Dale | 159
M Group for Thames Water | Kynance Mews | 10 | Road Closed with local diversion | 24-27/11/25 | Backup dates 01-04/12/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 160
Cadent Gas | Aubrey Walk | 22 | Road Closed with local diversion | 2025-11-30 | 2025-12-05 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 161
Thames Water | Carlyle Square | 7 | Road Closed with local diversion | 2025-12-01 | 2025-12-05 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Stanley | 162
Lanes Group PLC for Thames Water | Stadium Street | Whole Street | Road Closed with local diversion | 2026-01-05 | 2026-01-06 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Chelsea Riverside | 163
JSM Group Limited | Kensal Road | Ladbroke Grove | Road Closed with local diversion | TBA | TBA | From 8.00am on first day until 6.00pm on final day | Utility works |  | Golborne | 164
M Group for Thames Water | Mossop Street | Ives Street to First Street | Road Closed with local diversion | 23-27/02/26 | Backup Dates 02-06/03/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 165
|  |  |  | DEVELOPMENTS | [5 empty] | 166
Knight build Limited | Tryon Street | From outside of number 9 to the junction of the King's Road | Road Closure | 2025-08-11 | 2025-10-24 | Weekdays From 8.00am until 5.00pm | Developer works |  | Royal Hospital | 167
Neilcott Construction Ltd | Pelham Street | 40 | Footway Closure | 2025-08-18 | 2025-12-24 | Weekdays From 8.00am until 5.00pm | Developer works |  | Brompton and Hans Town | 168
Ant Yapi Uk | Earl's Court Road | 24, S/o Holland Park Gate | Footway Closure | 2025-09-29 | 2027-03-26 | Weekdays From 8.00am until 5.00pm | Developer works | Footway to be used as a loading Area | Abingdon | 169
Midgard City Limited | Newcombe Street | Junction of Kensington Place | Road Closure | 2025-08-27 | 2027-03-18 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Campden | 170
Neilcott Construction Ltd | Pelham Street | Brompton Road to Old Brompton Road | Westbourne Directional Road Closure | 2024-09-16 | 2026-02-09 | Weekdays From 8.00am on first day until 5.00pm on final day | Developer works |  | Brompton and Hans Town | 171
Fenton Civil Engineering | St Albans Grove | Stanford Road to Victoria Road | Road Closed with local diversion | 2025-12-18 | 2025-12-19 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 172
|  |  |  | MOBILE LIFTING OPERATIONS | [5 empty] | 173
Mechanical Movements and Enabling Services Limited | Wrights Lane | O/s Warner Music | Road closed with local diversion | 2025-10-11 | Backup Date 18/10/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 174
City Lifting Limited | Carlyle Square | 6 | Road closed with local diversion | 2025-10-14 | Backup Date 21/10/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Stanley | 175
Size Group Limited | Gilston Road | 14 | Road Width Reduced | 2025-10-17 | 2025-10-17 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 176
J &G Traffic Limited | The Little Boltons | 17 | Road Width Reduced | 2025-10-17 | Backup date 24/10/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 177
DE Group Contracting Limited | Lucan Place | 2 | Road Width Reduced | 2025-10-20 | Backup date 30/10/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 178
Mtec Warehousing Limited | Cadogan Place | 1 to 8 | Road Width Reduced | 2025-10-21 | 2026-10-21 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 179
Morgans Lifting Services Limited | Egerton Place | 11 to 12 | Road closed with local diversion | 2025-10-22 | 2025-10-23 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 180
First Choice Drainage Solutions Limited | Bevington Road | 6 | Road Width Reduced | 2025-10-22 | Backup date 29/10/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Golborne | 181
The Bakehouse Factory Limited | Kensington High Street | Various Locations | Road Width Reduced | 2025-10-22 | Backup date 29/10/25 | From 8.00pm to 6.00am | Mobile Lifting Operation | Nightworks | Various Wards | 182
Pretty Bird Limited | Golborne Road | 10 | Road Width Reduced | 2025-10-28 | 2025-10-28 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Golborne | 183
National Lifting Solutions Limited | Lucan Place | S/o 81 Fulham Road | Road Width Reduced | 28/09/25 to 04/10/25 | Backup Dates 05-11/10/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 184
City Lifting Limited | The Boltons | 9 | Road closed with local diversion | 2025-10-29 | Backup Date 30/10/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 185
Structural Glass Design | The Boltons | 24 | Road Width Reduced | 2025-10-29 | 2025-10-29 | From 7.00am to 12.00pm | Mobile Lifting Operation |  | Redcliffe | 186
Expectation Limited | Gertrude Street | And Hobury Street and Shalcomb Street | Road Width Reduced | 2025-10-29 | 2025-10-29 | From 8.00am to 600pm | Mobile Lifting Operation |  | Stanley | 187
Alexander Maltby Limited | Glebe Place | 23 to 25 | Road Width Reduced | 2025-10-29 | 2025-10-29 | From 8.00am to 600pm | Mobile Lifting Operation |  | Chelsea Riverside | 188
Lift Assist Limited | Addison Road | 77 | Road Width Reduced | 2025-10-29 | Backup Date 05/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Holland | 189
GRH Lifting Services Limited | Kensington High Street | Kensington Church Street to Old Court Place | Eastbound Directional Road closed with local diversion | 29-30/10/25 | Backup Date 30-31/10/25 | From 10.00pm to 6.00am | Mobile Lifting Operation | Nightworks | Campden | 190
Blade Traffic Management | Oxford Gardens | O/s Oxford Gardens primary School | Road closed with local diversion | 2025-10-30 | Backup Date 03/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Golborne | 191
National Lifting Solutions Limited | Blenheim Crescent | 135 | Road Width Reduced | 2025-10-30 | Backup Date 06/11/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 192
Victoria and Albert Museum | Exhibition Road | O/s Victoria and Albert Museum | Road Width Reduced | 2025-10-30 | Backup Date 06/11/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 193
YOO Serve Limited | Egerton Gardens | O/s Mortimer House | Road Width Reduced | 2025-10-31 | 2025-10-31 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 194
City Lifting Limited | Derry Street | O/s Northgate House | Road closed with local diversion | 01-02/11/25 | Backup Dates 8-9/11/25 | From 6.00am to 7.00pm | Mobile Lifting Operation |  | Queen's Gate | 195
Field and Lawn Limited | Kensington High Street | Various Locations | Road Width Reduced | 2025-11-02 | 2025-11-03 | From 9.00pm to 5.00am | Mobile Lifting Operation | Nightworks | Various Wards | 196
J &G Traffic Limited | Walton Street | Brompton Road to First Street | Road closed with local diversion | 03-04/11/25 | 07-08/01/26 | From 8.00pm to 5.00am | Mobile Lifting Operation | Nightworks | Brompton and Hans Town | 197
Chelci Group | Sloane Street | 203 | Road Width Reduced | 2025-11-04 | 2025-11-04 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 198
City Lifting Limited | The Little Boltons | 13 to 15 | Road closed with local diversion | 2025-11-05 | Backup Date 12/11/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 199
Blachere illuminations Limited | King's Road | O/s 52 to O/s 187 | Road Width Reduced | 2025-11-06 | 2025-11-07 | From 8.00pm until 6.00am | Mobile Lifting Operation | Nightworks | Royal Hospital | 200
Falcon Tower Crane Services Limited | Barlby Road | Ladbroke Grove to Admiral Mews | Road closed with local diversion | 08-09/11/25 | Backup Dates 15-16/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Dalgarno | 201
Nationwide Traffic Solutions Limited | Sloane Square | O/s Peter Jones Store | Road Width Reduced | 2025-11-08 | Backup date 16/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Royal Hospital | 202
Lift Assist Limited | Holland Villas Road | 11 | Road closed with local diversion | 2025-11-10 | Backup Date 18/11/25 | From 8.00am to 5.00pm | Mobile Lifting Operation |  | Holland | 203
Chevron Traffic Management | Sloane Street | Whole Street | Road Width Reduced | 2025-11-11 | 2025-11-12 | From 9.00pm until 6.00am | Mobile Lifting Operation | Nightworks | Brompton and Hans Town | 204
City Lifting Limited | The Boltons | 15 | Road closed with local diversion | 2025-11-13 | Backup Date 14/11/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 205
Paragon Traffic Management Limited | Fulham Road | 260 | Temporary Traffic Signals and Road Width Reduced | 2025-11-16 | 2025-11-16 | From 9.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 206
Structural Glass Design | The Boltons | 24 | Road closed with local diversion | 2025-11-17 | Backup Date 25/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 207
Chelci Group | Sloane Street | 203 | Road Width Reduced | 2025-11-18 | 2025-11-19 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 208
Chevron TM | Cathcart Road | O/s Cathcart House | Road closed with local diversion | 2025-11-19 | Backup Date 20/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 209
City Lifting Limited | The Boltons | 9 | Road closed with local diversion | 2025-11-19 | Backup Date 20/11/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 210
Fitzgerald Builders Limited | Cranley Gardens | 17 to 33 | Road Width Reduced | 2025-11-23 | 2025-11-23 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Courtfield | 211
City Lifting Limited | The Little Boltons | 6 | Road closed with local diversion | 2025-11-26 | Backup Date 04/12/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 212
Fixer CMG Limited | Bassett Road | Whole Road | Road closed with local diversion | 2025-11-27 | 2025-11-28 | From 6.00am to 11.00pm | Mobile Lifting Operation |  | St Helens | 213
Lift Assist Limited | Earl's Court Square | 35 to 37 | Road Width Reduced | 2025-12-17 | Backup date 13/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Earl's Court | 214
Assured Traffic Solutions | Sydney Street | Jnc King's Road | Road closed with local diversion | 2026-01-04 | Backup Date 11/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Stanley | 215
Heathrow Cranes Limited | Earl's Court Road | Kensington High Street to Pater Street | Road closed with local diversion | 10-11/01/26 | Backup Dates 17-18/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 216
Marjen Limited on behalf of Waldon Telecoms | Lancaster Road | Ladbroke Grove to 87 Lancaster Road | Road closed with local diversion | TBC | TBC | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Colville | 217
|  |  |  | LOCAL RESIDENTS - STREET PARTIES & SPECIAL EVENTS | [5 empty] | 218
RBKC | Portobello Road | Colville Terrace to Oxford Gardens | Road Closed for a Street Market | 2025-06-22 | 2025-12-21 | Closed on Sundays From 8.00am until 5.00pm | Road Closed for a Street Market | Closed on Sundays | Colville and Golborne | 219
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-10-22 | 2025-10-22 | From 6.30pm until 11.00pm | Chelsea V AFC Ajax | Large amount of Pedestrians going to a football match | Various Wards | 220
RBKC | Phillimore Walk | Hornton Street to Campden Hill Road | Road Closed for a Street Market | 2025-10-25 | 2025-10-25 | From 7.30am until 7.30pm | Road Closed for a Street Market |  | Campden | 221
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-10-25 | 2025-10-25 | Between 12.30pm and 5.00pm | Chelsea V Sunderland | Large amount of Pedestrians going to a football match | Various Wards | 222
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-01 | 2025-11-01 | Between 10.30am and 3.00pm | Chelsea Women V London City Lionesses | Large amount of Pedestrians going to a football match | Various Wards | 223
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-08 | 2025-11-08 | Between 6.30pm and 11.00pm | Chelsea V Wolverhampton Wanderers | Large amount of Pedestrians going to a football match | Various Wards | 224
RBK&C | Kensington High Street | Kensington Church Street | Road Closures | 2025-11-09 | 2025-11-09 | From 9.30am to 12.30pm | Remembrance Service |  | Campden | 225
Cadogan Estate Limited | King's Road | Sloane Square to Walpole Street | Road Closed for a Community Event | 2025-11-15 | 2025-11-15 | From 7.00am until 8.00pm | Community Street party | Turning on the Christmas Lights | Royal Hospital | 226
Cadogan Estate Limited | Holbein Place | from Sloane Square | Road Closed for a Community Event | 2025-11-15 | 2025-11-15 | From 12.00am until 7.00pm | Community Street party |  | Royal Hospital | 227
Run Italy | Kensington High Street, Abbotsbury Road Holland Park, Ilchester Place | Various Road Closures and an eastbound directional road closure of Kensington High Street. | Various Road Closures and an eastbound directional road closure of Kensington High Street. | 2025-11-23 | 2025-11-23 | From 07.30am until 10.30am | Roads Closed for a Fun Run | Fun Run | Campden and Holland | 228
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-25 | 2025-11-25 | From 6.30pm until 11.00pm | Chelsea V FC Barcelona | Large amount of Pedestrians going to a football match | Various Wards | 229
RBKC | Phillimore Walk | Hornton Street to Campden Hill Road | Road Closed for a Street Market | 2025-11-29 | 2025-11-29 | From 7.30am until 7.30pm | Road Closed for a Street Market |  | Campden | 230
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-30 | 2025-11-30 | Between 3.00pm and 7.00pm | Chelsea V Arsenal | Large amount of Pedestrians going to a football match | Various Wards | 231
Restart Lives | Lennox Gardens | S/o St Columba's Church | Road Closed for a Charity Event | 05-06/12/25 | Backup dates 09-10/12/25 | From 6.00pm until 7.00am | Charity Event | Road Closed Overnight to stage this event | Brompton and Hans Town | 232
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-13 | 2025-12-13 | Between 12.30pm and 5.00pm | Chelsea V Everton | Large amount of Pedestrians going to a football match | Various Wards | 233
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-28 | 2025-12-28 | Between 12.30pm and 5.00pm | Chelsea V Aston Villa | Large amount of Pedestrians going to a football match | Various Wards | 234
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-01 | 2026-01-01 | Between 16.00pm and 9.00pm | Chelsea V Bournemouth | Large amount of Pedestrians going to a football match | Various Wards | 235
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-17 | 2026-01-17 | Between 12.30pm and 5.00pm | Chelsea V Brentford | Large amount of Pedestrians going to a football match | Various Wards | 236
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-21 | 2026-01-21 | From 6.30pm until 11.00pm | Chelsea V Pafos FC | Large amount of Pedestrians going to a football match | Various Wards | 237
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-24 | 2026-01-24 | Between 11.00am and 3.00pm | Chelsea Women V Arsenal | Large amount of Pedestrians going to a football match | Various Wards | 238
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-31 | 2026-01-31 | Between 12.30pm and 5.00pm | Chelsea V West Ham United | Large amount of Pedestrians going to a football match | Various Wards | 239
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-02-11 | 2026-02-11 | Between 18.00pm and 11.00pm | Chelsea V Leeds United | Large amount of Pedestrians going to a football match | Various Wards | 240
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-02-21 | 2026-02-21 | Between 12.30pm and 5.00pm | Chelsea V Burnley | Large amount of Pedestrians going to a football match | Various Wards | 241
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-03-14 | 2026-03-14 | Between 12.30pm and 5.00pm | Chelsea V Newcastle United | Large amount of Pedestrians going to a football match | Various Wards | 242
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-04-11 | 2026-04-11 | Between 12.30pm and 5.00pm | Chelsea V Manchester City | Large amount of Pedestrians going to a football match | Various Wards | 243
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-04-18 | 2026-04-18 | Between 12.30pm and 5.00pm | Chelsea V Manchester United | Large amount of Pedestrians going to a football match | Various Wards | 244
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-02 | 2026-05-02 | Between 12.30pm and 5.00pm | Chelsea V Nottingham Forest | Large amount of Pedestrians going to a football match | Various Wards | 245
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-16 | 2026-05-16 | Between 12.30pm and 5.00pm | Chelsea Women V Manchester United | Large amount of Pedestrians going to a football match | Various Wards | 246
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-17 | 2026-05-17 | Between 12.30pm and 5.00pm | Chelsea V Tottenham Hotspur | Large amount of Pedestrians going to a football match | Various Wards | 247
|  |  |  | LOCAL ACTIVITIES ON THE TFL, HAMMERSMITH & FULHAM, WESTMINSTER OR BRENT NETWORKS | [5 empty] | 248
Thames Water | Holland Road | Napier Place to Holland Gardens | Lane Closure | 01,04,11,25/10/25 | 01,04,11,25/10/25 | From 8.00am to 12.00pm | Maintenance Works |  | Holland | 249
TfL | Battersea Bridge | North Side of the River | Lane and Junction restrictions | 05-06, 12-13,19-22 /10/2025 | 05-06, 12-13,19-22 /10/2025 | From 8.00pm until 6.00am each Night | Junction improvement works | Nightworks | Chelsea Riverside | 250
Cadent Gas | North Pole Road | Junction of Scrubs lane and Woods Lane | Three Way Lights | 2025-10-13 | 2025-11-10 | From 8.00am on first day until 6.00pm on final day | Utility works | Expect Long Traffic Delays in the Area | LBH&F | 251
TfL | Knightsbridge | Piccadilly Underpass | Westbound Directional Road Closure | 17-20 & 24-27/10/25 & 31/10/25 to 03/11/25 | 17-20 & 24-27/10/25 & 31/10/25 to 03/11/25 | From 8.00pm on the first day until 05.00am on the final day | Maintenance Works |  | Westminster | 252
TfL | West Cromwell Road | Warwick Road to North End Road | Westbound Directional Road Closure | 2025-10-24 | 2025-10-27 | From 11.00pm on the first day until 05.00am on the final day | London Underground Works | Road Closed Westbound to allow a crane operation from the bridge down over the Railway Lines | Earl's Court | 253
Marjen Limited | Battersea Bridge | South side of the River | Bridge and Road Closure | 2025-10-26 | 2025-10-27 | From 8.00am on first day until 5.00am on final day | Crane Operation | All Day and Overnight | Wandsworth | 254
Westminster | Pimlico Road | Ebury Bridge Road | Westbound Directional Road Closure | 26-27/10/25 | Backup dates 27-28/10/25 | From 10.00pm until 6.00am | Resurfacing | Night Works | Westminster | 255
LB Wandsworth | Battersea Park | Roads Surrounding Battersea Park | Road Closures and the closure of Albert Bridge | 2025-11-01 | 2025-11-02 | Saturday 1st (Road Closures 5.00pm to 11.00pm), Sunday 3rd (Road Closures 4.00pm to 10.00pm) | Event |  | LB Wandsworth | 256
Marjen Limited | Battersea Bridge | South side of the River | Bridge and Road Closure | 2025-11-03 | Backup date 09/11/25 | From 8.00am on first day until 5.00am on final day | Crane Operation | All Day and Overnight | Wandsworth | 257
Royal Albert Hall | Kensington Gore | Prince Consort Road, Bremner Road, Jay Mews | Roads Closed around the Royal Albert Hall | 2025-11-06 | 2025-11-10 | From 8.00pm until 1.00am each night | Festival of Remembrance |  | Westminster | 258
Royal Albert Hall | Kensington Gore | Prince Consort Road, Bremner Road, Jay Mews | Roads Closed around the Royal Albert Hall | 2025-11-08 | 2025-11-08 | From 6.00am until 1.00am | Festival of Remembrance |  | Westminster | 259
TfL | Knightsbridge | Piccadilly Underpass | Eastbound Directional Road Closure | 7-10 & 14-17 & 21-24/11/25 | 7-10 & 14-17 & 21-24/11/25 | From 8.00pm on the first day until 05.00am on the final day | Maintenance Works |  | Westminster | 260
Cadent Gas | North Pole Road | Junction of Scrubs lane to Du Cane Road | Southbound Directional Road Closure with diversion | 2025-11-10 | 2025-12-22 | From 8.00am on first day until 6.00pm on final day | Utility works | Expect Long Traffic Delays in the Area | LBH&F | 261
| Redcliffe Gardens | 110 | Footway Closed with a lane closure | 2025-11-22 | 2025-11-23 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Redcliffe | 262
The Royal Albert Hall | Kensington Gore | Prince Consort Road, Bremner Road, Jay Mews | Roads Closed for an event | 2025-11-30 | 2025-12-01 | From 12.00pm on the first day until 11.59pm on the last day | Fashion Awards |  | Westminster | 263
Cadent Gas | Wood Lane | North Pole Road to Du Cane Road | Southbound Directional Road Closed with local diversion | 2025-11-30 | 2025-12-21 | From 8.00am on first day until 6.00pm on final day | Utility works |  | LBH&F | 264
Thames Water | Eaton Gate | Eaton Square to Clivedon Place | Road Closed Local Diversions | 2025-11-13 | 2025-11-14 | From 0.00am on first day until 11.59pm on final day | Utility works |  | City of Westminster | 265
Thames Water | Brompton Road | Jnc Beauchamp Place | Westbound lanes 2 and 3 closed | 2025-12-14 | 2025-12-15 | From 11.00pm until 5.00am each Night | Utility works | Nightworks | Brompton and Hans Town | 266
Westminster | Knightsbridge | Trevor Road to Brompton road | Eastbound Directional Road Closure | 2026-01-06 | 2026-01-07 | From 10.00pm until 6.00am | Resurfacing Works |  | Westminster | 267
Costain for TfL | A40 Westway | Westway Roundabout | Eastbound Weekend Closures | 2026-01-09 | 2026-03-23 | From 10.00pm on Friday night until 5.00am on the Monday Morning | Bridge Maintenance Works |  | Notting Dale | 268
Costain for TfL | A40 Westway | Marylebone Flyover | Eastbound Weekend Closures | 2026-01-19 | 2026-03-13 | Various Weekend and some weeknight closures | Bridge Maintenance Works |  | Westminster | 269
Costain for TfL | A40 Westway | Marylebone Flyover | Full A40 Closure | 2026-03-27 | 2026-04-29 | Various Weekend and some weeknight closures | Bridge Maintenance Works |  | Westminster | 270
Costain for TfL | A40 Westway | Marylebone Flyover | Westbound Weekend Closures | 2026-04-29 | 2026-05-28 | Various Weekend and some weeknight closures | Bridge Maintenance Works |  | Westminster | 271
Costain for TfL | A40 Westway | Westway Roundabout | Westbound Weekend Closures | 2026-03-27 | 2026-06-22 | From 10.00pm on Friday night until 5.00am on the Monday Morning (Excluding Bank Holiday Weekends) | Bridge Maintenance Works |  | Notting Dale | 272
Costain for TfL | Harrow Road | Edgware Road | Nighttime Road Closures | TBA | TBA | From 10.00pm until 5.00am | Resurfacing Works |  | Westminster | 273
This list is not an exhaustive list of all works that are being carried out across the Borough.
For full details of all works being carried out in the borough please use the London Works facility using the following link:
http://one.network