## Sheet1
Royal Borough of Kensington and Chelsea Works and Events Bulletin - 20th November 2025
Works Originator | Road | Location | Effect | From Date | To Date | Time | Reason | Comment | Council Ward | Line Number
|  |  |  | RBKC Footway Work | [5 empty] | 3
Royal Borough of Kensington and Chelsea | Highlever Road | 154-148 , (Remaining FW) | Footway Closed with local diversion | 2025-09-01 | 2025-12-15 | From 8.00am to 5.00pm | Footway improvement works |  | Dalgarno | 4
Royal Borough of Kensington and Chelsea | Sirdar Road | Treadgold - 27 Wilsham Street | Footway Closed with local diversion | 2025-09-22 | 2026-02-03 | From 8.00am to 5.00pm | Footway improvement works |  | Notting Dale | 5
Royal Borough of Kensington and Chelsea | Cadogan Square | Opposite 3 to 13 and from lamp post 002 to Pont Street (WFW) and opposite 71-72 (NFW |  | 2025-09-29 | 2026-02-12 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 6
Royal Borough of Kensington and Chelsea | Cheyne Walk | Cheyne Mews to Royal Hospital Road (NFW) |  | 2025-10-13 | 2025-12-17 | From 8.00am to 5.00pm | Footway improvement works |  | Royal Hospital | 7
Royal Borough of Kensington and Chelsea | St Lawrence Terrace | Chesterton Road junction to no.18 (EFW) and (WFW) at end of no. 38 Oxford Gardens to end of no. 21 | Footway Closed with local diversion | 2025-10-13 | 2025-11-27 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 8
Royal Borough of Kensington and Chelsea | Cadogan Place | Opposite 31-47 and 58 to Cadogan Place (WFW) |  | 2025-10-20 | 2025-12-04 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 9
Royal Borough of Kensington and Chelsea | Chesterton Road | St Lawrence Terrace to Portobello Road (both sides) | Footway Closed with local diversion | 2025-10-29 | 2025-12-16 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 10
Royal Borough of Kensington and Chelsea | Southwell Gardens | From Grenville Place to the Church gate (SFW) |  | 2025-11-04 | 2025-11-27 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 11
Royal Borough of Kensington and Chelsea | Colville Gardens | Colville Terrace to Talbot Road (EFW) | Footway Closed with local diversion | 2025-11-11 | 2025-12-03 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 12
Royal Borough of Kensington and Chelsea | Pont Street | Outside 31-39 and road side footway between Cadogan Square and Cadogan Square (SFW) |  | 2025-11-11 | 2025-12-08 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 13
Royal Borough of Kensington and Chelsea | Pelham Crescent | Pelham Place to Fulham Road | Footway Closed with local diversion | 2025-11-13 | 2025-12-11 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 14
Royal Borough of Kensington and Chelsea | Jameson Street | Kensington Place to Uxbridge Street (WFW) | Footway Closed with local diversion | 2025-11-20 | 2025-12-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 15
Royal Borough of Kensington and Chelsea | Jameson Street | Kensington Place to Uxbridge Street (WFW) |  | 2025-11-20 | 2025-12-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 16
Royal Borough of Kensington and Chelsea | Smith Street | 1 to 10 ( incl. 1-7 Durham Place) (SFW) |  | 2025-11-28 | 2025-12-15 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 17
Royal Borough of Kensington and Chelsea | Colville Terrace | Colville Gardens to Powis Square (NFW) | Footway Closed with local diversion | 2025-12-04 | 2025-12-15 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 18
Royal Borough of Kensington and Chelsea | Ladbroke Road | Ladbroke Terrace to Kensington Park Road (NFW) | Footway Closed with local diversion | 2026-01-05 | 2026-02-26 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 19
Royal Borough of Kensington and Chelsea | Victoria Road | End to St Alban's Grove - (EFW) |  | 2026-01-05 | 2026-02-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 20
Royal Borough of Kensington and Chelsea | Doyley Place | Outside Wilbraham House to Mansion House (EFW) |  | 2026-01-05 | 2026-02-06 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 21
Royal Borough of Kensington and Chelsea | Hillsleigh Road | Aubrey Walk to Campden Hill Square (WFW) and outside 16-17 (EFW) | Footway Closed with local diversion | 2026-01-06 | 2026-02-20 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 22
Royal Borough of Kensington and Chelsea | Aubrey Walk | Outside 14 to Hillsleigh Road (NFW) | Footway Closed with local diversion | 2026-01-06 | 2026-02-20 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 23
Royal Borough of Kensington and Chelsea | Berkeley Gardens | Kensington Church Street (SFW) from no. 104 to no. 7 and (NFW) no. 106 to 21b Brunswick Gardens | Footway Closed with local diversion | 2026-01-06 | 2026-01-26 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 24
Royal Borough of Kensington and Chelsea | Norland Road | 22-24 Norland Road/ Shepherds Bush underpass |  | 2026-01-06 | 2026-03-02 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 25
Royal Borough of Kensington and Chelsea | Ladbroke Grove WFW | Cornwall Crescent to Lancaster Road | Footway Closed with local diversion | 2026-01-07 | 2026-03-03 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 26
Royal Borough of Kensington and Chelsea | Kensington Church Street | Kensington Mall to Notting Hill Gate (EFW) | Footway Closed with local diversion | 2026-01-07 | 2026-02-09 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 27
Royal Borough of Kensington and Chelsea | Kensington Church Walk | Outside Macmillan House to end of paved surfacing at church |  | 2026-01-07 | 2026-03-17 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 28
Royal Borough of Kensington and Chelsea | Campden Hill Square | Opposite 24 to Holland Park Ave (WFW) and no.16 to Hillsleigh Road (SFW) | Footway Closed with local diversion | 2026-01-12 | 2026-02-12 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 29
Royal Borough of Kensington and Chelsea | Queens Gate | Cromwell Road to Queen's Gate Place (WFW) |  | 2026-01-12 | 2026-03-20 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 30
Royal Borough of Kensington and Chelsea | Morgan Road | Wornington Road to St Ervans Road (both sides) | Footway Closed with local diversion | 2026-01-26 | 2026-02-13 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 31
Royal Borough of Kensington and Chelsea | Morgan Road | Wornington Road to St Ervans Road (both sides) |  | 2026-01-26 | 2026-02-13 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 32
Royal Borough of Kensington and Chelsea | Brunswick Gardens | Outside 11 to 33 Berkely Gardens WFW + opposite to 3-7 (both sides) WFW | Footway Closed with local diversion | 2026-01-27 | 2026-02-18 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 33
Royal Borough of Kensington and Chelsea | Wilbraham Place | Outside 9/9a to D'Oyley Place(NFW) |  | 2026-02-09 | 2026-02-17 | From 8.00am to 5.00pm | Footway improvement works |  | Royal Hospital | 34
Royal Borough of Kensington and Chelsea | Notting Hill Gate | O/S 34 - Linden Gardens - NFW | Footway Closed with local diversion | 2026-02-10 | 2026-03-09 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 35
Royal Borough of Kensington and Chelsea | Aubrey Road | Outside 8c to Holland Park Road (WFW) and no. 29 to Holland Park Road (EFW) | Footway Closed with local diversion | 2026-02-13 | 2026-04-09 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 36
Royal Borough of Kensington and Chelsea | Elkstone Road | Between lamp posts 010 and 016 (NFW) |  | 2026-02-16 | 2026-03-19 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 37
Royal Borough of Kensington and Chelsea | Draycott Avenue | Outside Nell Gwynn House trade entrance SFW and NFW at Cadogan Street and opposite Mossop St (SFW) |  | 2026-02-18 | 2026-03-11 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 38
Royal Borough of Kensington and Chelsea | Campden Hill Gardens | Opposite no 15 to Campden Hill Road (WFW)Opposite no 15 to Campden Hill Road (WFW) | Footway Closed with local diversion | 2026-02-19 | 2026-03-12 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 39
Royal Borough of Kensington and Chelsea | Kensington Mall | Kensington Church Street to Palace Garden Terrace (SFW) | Footway Closed with local diversion | 2026-02-19 | 2026-02-27 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 40
Royal Borough of Kensington and Chelsea | Palace Gardens Terrace | Outside 82-102 and 60-64 - (EFW) | Footway Closed with local diversion | 2026-03-02 | 2026-03-25 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 41
Royal Borough of Kensington and Chelsea | Kensington Church St | Holland Street to Holland Place (WFW) |  | 2026-03-02 | 2026-04-01 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 42
Royal Borough of Kensington and Chelsea | Gloucester Road | Kynance Place to Victoria Road (WFW) |  | 2026-03-03 | 2026-04-01 | From 8.00am to 5.00pm | Footway improvement works |  | Queen's Gate | 43
Royal Borough of Kensington and Chelsea | Westbourne Park Road | Ladbroke Grove to opposite 338 - SFW | Footway Closed with local diversion | 2026-03-04 | 2026-03-16 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 44
Royal Borough of Kensington and Chelsea | Ladbroke Grove | Outside 2 to 4 (EFW) | Footway Closed with local diversion | 2026-03-10 | 2026-03-30 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 45
Royal Borough of Kensington and Chelsea | Ixworth Place | Opposite Pond Place to Marlborough Crescent and (SFW) and at Pond Place (NFW) |  | 2026-03-12 | 2026-03-19 | From 8.00am to 5.00pm | Footway improvement works |  | Stanley | 46
Royal Borough of Kensington and Chelsea | Upper Cheyne Row | Oakley Street to Cheyne Row (SFW) |  | 2026-03-17 | 2026-03-25 | From 8.00am to 5.00pm | Footway improvement works |  | Chelsea Riverside | 47
Royal Borough of Kensington and Chelsea | Fulham Road | Dovehouse Street to opposite Sumner Place (SFW) |  | 2026-03-23 | 2026-04-02 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 48
|  |  |  | RBKC WEEKDAY RESURFACING | [5 empty] | 49
Royal Borough of Kensington and Chelsea | Dalgarno Way | Lamp 0014 to 0018 Sutton Way (corner) - Table Top | Road Closure | 2025-12-01 | 2025-12-01 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Dalgarno | 50
Royal Borough of Kensington and Chelsea | Dalgarno Way | Dalgarno Gardens to No.6 | Road Closure | 2025-12-01 | 2025-12-01 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Dalgarno | 51
Royal Borough of Kensington and Chelsea | Lansdowne Rise | Clarendon Road - Lansdown Crescent |  | 2025-12-02 | 2025-12-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 52
Royal Borough of Kensington and Chelsea | Lansdowne Road | Lansdowne Rise - St John Gardens |  | 2025-12-02 | 2025-12-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 53
Royal Borough of Kensington and Chelsea | St Johns Gardens | Clarendon Road - Ladbroke Grove | Road Closure | 2025-12-04 | 2025-12-05 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 54
Royal Borough of Kensington and Chelsea | Hillgate Place | Outside 73-77 to Jameson Street |  | 2026-01-12 | 2026-01-12 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 55
Royal Borough of Kensington and Chelsea | Denbigh Road | From 16 to Westbourne Grove | Road Closure | 2026-01-13 | 2026-01-13 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 56
Royal Borough of Kensington and Chelsea | All Saints Road | Tavistock Rd to Tavistock Crescent | Road Closure | 2026-01-14 | 2026-01-14 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 57
Royal Borough of Kensington and Chelsea | Tavistock Road | Junction at All Saint's Road | Road Closure | 2026-01-14 | 2026-01-14 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 58
Royal Borough of Kensington and Chelsea | Tavistock Crescent | All Saint's Road to St Luke's Road | Road Closure | 2026-01-14 | 2026-01-14 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 59
Royal Borough of Kensington and Chelsea | Farm Place | From Hillgate Place to Uxbridge Road |  | 2026-01-16 | 2026-01-16 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 60
Royal Borough of Kensington and Chelsea | Hornton Street | Holland Street to Gloucester Walk | Road Closure | 2026-01-26 | 2026-01-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 61
Royal Borough of Kensington and Chelsea | Holland Street | Campden Hill Road to Hornton Street | Road Closure | 2026-01-26 | 2026-01-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 62
Royal Borough of Kensington and Chelsea | Sloane Avenue | No. 22 to Draycott Place and Anderson Street | Road Closure | 2026-01-28 | 2026-01-28 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 63
Royal Borough of Kensington and Chelsea | Draycott Place | Between Sloane Avenue and O/S no. 57 | Road Closure | 2026-01-28 | 2026-01-28 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 64
Royal Borough of Kensington and Chelsea | Grenville Place | From No. 3 to Cornwall Gardens Junction | Road Closure | 2026-01-30 | 2026-01-30 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 65
Royal Borough of Kensington and Chelsea | Emperor's Gate | From Grenville Place to end of no. 6 | Road Closure | 2026-01-30 | 2026-01-30 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 66
Royal Borough of Kensington and Chelsea | Southwell Gardens | Grenville Place to no. 8 Southwell Gardens | Road Closure | 2026-01-30 | 2026-01-30 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 67
Royal Borough of Kensington and Chelsea | Sydney Street | Cale Street to Fulham Road | Road Closure | 2026-02-02 | 2026-02-02 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 68
Royal Borough of Kensington and Chelsea | Cale Street | Dovehouse Road to Sydney Street | Road Closure | 2026-02-03 | 2026-02-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 69
Royal Borough of Kensington and Chelsea | Holbein Place | Pimlico Road to Graham Terrace, Whittaker St to Sloane Gardens | Road Closure | 2026-02-04 | 2026-02-04 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 70
Royal Borough of Kensington and Chelsea | Cadogan Gate | Sloane Street to Cadogan Square | Road Closure | 2026-02-06 | 2026-02-06 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 71
Royal Borough of Kensington and Chelsea | Bedford Gardens | Campden Hill Road to Kensington - 4x humps | Road Closure | 2026-02-09 | 2026-02-11 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Campden | 72
Royal Borough of Kensington and Chelsea | Egerton Terrace | Egerton Place to Egerton Gardens | Road Closure | 2026-02-12 | 2026-02-13 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 73
Royal Borough of Kensington and Chelsea | Egerton Gardens | Egerton Crescent to Egerton Terrace | Road Closure | 2026-02-12 | 2026-02-13 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 74
Royal Borough of Kensington and Chelsea | St Leonards Terrace | Smith Street to Cheltenham Terrace | Road Closure | 2026-02-16 | 2026-02-18 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 75
Royal Borough of Kensington and Chelsea | Flood Street | Royal Hospital Road to no. 77 | Road Closure | 2026-02-19 | 2026-02-20 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Chelsea Riverside | 76
Royal Borough of Kensington and Chelsea | St Lawrence Terrace | Oxford Gardens to Chesterton Rd | Road Closure | 2026-02-23 | 2026-02-26 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Golborne | 77
Royal Borough of Kensington and Chelsea | Westbourne Grove | Denbigh Road to Ledbury Road | Road Closure | 2026-02-24 | 2026-02-24 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Colville | 78
Royal Borough of Kensington and Chelsea | Cadogan Gardens | Cadogan Gardens to Cadogan Gardens | Road Closure | 2026-02-25 | 2026-02-25 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 79
Royal Borough of Kensington and Chelsea | Cadogan Gardens | Cadogan Gardens to Cadogan Gardens | Road Closure | 2026-02-25 | 2026-02-25 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Brompton and Hans Town | 80
Royal Borough of Kensington and Chelsea | D'Oyley Street | Lamp post 001 to Sloane Gate Mansion | Road Closure | 2026-02-26 | 2026-02-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 81
Royal Borough of Kensington and Chelsea | Ellis Street | From Sloane Street to 11/12 Ellis street | Road Closure | 2026-02-26 | 2026-02-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 82
Royal Borough of Kensington and Chelsea | Gloucester Road | o/s no. 110 to o/s 57 and o/s nos. 39/41 to no. 5 | Road Closure | 2026-02-26 | 2026-02-27 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 83
Royal Borough of Kensington and Chelsea | Pond Place | From end to Fulham Road | Road Closure | 2026-03-02 | 2026-03-02 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 84
Royal Borough of Kensington and Chelsea | Bury Walk | between nos. 43 to 49 | Road Closure | 2026-03-02 | 2026-03-02 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Stanley | 85
Royal Borough of Kensington and Chelsea | Ladbroke Road | Horbury Crescent to Kensington Park Road | Road Closure | 2026-03-03 | 2026-03-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Pembridge | 86
Royal Borough of Kensington and Chelsea | Stanford Road | from end to St Alban's Grove | Road Closure | 2026-03-04 | 2026-03-04 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Queen's Gate | 87
|  |  |  | RBKC STREET LIGHTING | [5 empty] | 88
89
|  |  |  | RBKC WEEKEND WORKS | [5 empty] | 90
91
|  |  |  | RBKC NIGHT RESURFACING | [5 empty] | 92
Royal Borough of Kensington and Chelsea | Cromwell Place | Old Brompton Road to Thurloe Place | Road Closure | 2026-02-05 | 2026-02-05 | From 8.00PM to 6.00AM | Carriageway Resurfacing | Nightworks | Brompton and Hans Town | 93
Royal Borough of Kensington and Chelsea | Sloane Square | Sloane Street to Lower Sloane Street | Road Closure | TBA | TBA | From 8.00PM to 6.00AM | Carriageway Resurfacing | Nightworks | Royal Hospital | 94
|  |  |  | RBKC DRAINAGE WORKS | [5 empty] | 95
Royal Borough of Kensington and Chelsea | Ives Street | 13-15 | Road Closure | 17/11/25 | 21/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | Brompton & Hans Town | 96
Royal Borough of Kensington and Chelsea | Mulberry Walk | 11-13 | Road Width Reduced | 19/11/25 | 25/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | Stanley | 97
Royal Borough of Kensington and Chelsea | Elm Park Gardens | 56 | Road Width Reduced | 21/11/25 | 25/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | Stanley | 98
Royal Borough of Kensington and Chelsea | Ladbroke Walk | 8a | Road Closure | 24/11/25 | 28/11/26 | From 8.00 am to 5.00pm | Gully repair works |  | Pembridge | 99
Royal Borough of Kensington and Chelsea | Dukes Lane | 1-6 Dukes Lane Mansions | Road Closure | 25/11/25 | 01/12/25 | From 8.00 am to 5.00pm | Gully repair works |  | Campden | 100
Royal Borough of Kensington and Chelsea | Cornwall Mews South | 14 | Road Width Reduced | 26/11/25 | 28/11/25 | From 8.00 am to 5.00pm | Gully repair works |  | Queens Gate | 101
Royal Borough of Kensington and Chelsea | Highlever Road | 52-54 | Road Width Reduced | 27/11/25 | 03/12/25 | From 8.00 am to 5.00pm | Gully repair works |  | St Helens | 102
Royal Borough of Kensington and Chelsea | Elvaston Mews | 25 | Road Width Reduced | 27/11/25 | 02/12/25 | From 8.00 am to 5.00pm | Gully repair works |  | Queens Gate | 103
|  |  |  | RBKC SPECIAL ENGINEERING PROJECTS | [5 empty] | 104
Royal Borough of Kensington and Chelsea | Albert Bridge | On The Bridge | Directional Road Closures | 2025-12-05 | 2025-12-05 | Between 8.00am on first day until 6.00pm on final day. | Maintenance Works | Southbound Directional Closure in the morning, followed by a northbound directional closure in the afternoon. | Chelsea Riverside | 105
Royal Borough of Kensington and Chelsea | Ensor Mews | Jnc Cranley Gardens | Road Closed with local diversion | 2025-08-27 | 2025-12-10 | Between 8.00am on first day until 6.00pm on final day. | Repair works to Archway |  | Courtfield | 106
Royal Borough of Kensington and Chelsea | Kensington Park Road | Between it's junctions with Elgin Crescent & Blenheim Crescent | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 29/09/25 | 16/06/26 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Coville | 107
Royal Borough of Kensington and Chelsea | Sidar Road | At it's junctions with Mary Place and Wilsham Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 27/10/25 | 21/11/25 | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Notting Dale | 108
Royal Borough of Kensington and Chelsea | Gloucester Road | Between its junctions with Stanhope Gardens, Courtfield Road & A4 Cromwell Road | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 03/11/25 | 10/07/26 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Courtfield | 109
Royal Borough of Kensington and Chelsea | Clarendon Road | At it's junctions with Dulford Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 2026-02-09 | 2026-03-13 | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Notting Dale | 110
Royal Borough of Kensington and Chelsea | Albert Bridge | Bridge Closure | Bridge Closed for maintenance works | 2026-07-20 | 2026-09-14 | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Bridge maintenance works | Chelsea Riverside | 111
Royal Borough of Kensington and Chelsea | Elm Park Gardens | At it's junctions with Elm Park Road and Fulham Road | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 2025-12-01 | 2025-12-12 | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Tree islands) | Stanley | 112
Royal Borough of Kensington and Chelsea | Lower Sloane Street | Junction with Sloane Square | Southbound Directional Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 113
Royal Borough of Kensington and Chelsea | Lower Sloane Street | Junction with Sloane Square | Northbound Directional Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 114
Royal Borough of Kensington and Chelsea | Harrington Gardens | At it's junctions with Collingham Gardens | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Courtfield | 115
Royal Borough of Kensington and Chelsea | Ladbroke Square | At it's junctions with Ladbroke Terrace | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Speed Humps) | Pembridge | 116
Royal Borough of Kensington and Chelsea | Queen's Gate | At it's junctions with Elvaston Place / TBC | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Speed Humps) | Queen's Gate | 117
Royal Borough of Kensington and Chelsea | Sidar Road | At it's junctions with Mary Place and Wilsham Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Notting Dale | 118
Royal Borough of Kensington and Chelsea | Silchester Road | At it's junctions with Lancaster Road | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Improvement Works (Carriageway) | Notting Dale | 119
Royal Borough of Kensington and Chelsea | St Quintins Avenue | At it's junctions with Pangbourne Avenue & Wallingford Avenue | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Dalgarno & St Helens | 120
|  |  |  | UTILITY COMPANY WORKS | [5 empty] | 121
Barhale for Thames Water | Pont Street | S/o Green Taxi Hut Jnc Cadogan Place | Lane Restrictions - Chicane | 2025-10-01 | 2025-12-02 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 122
M Group for Thames Water | Sydney Street | Fulham Road to outside 16 | Road Closed with local diversion | 27/10/25 to 05/11/25 | Backup Dates 21-30/11/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Stanley | 123
Cappagh for Thames Water | Elm Park Road | Jnc Beaufort Street | Road Closed with local diversion | 2025-11-07 | 2025-11-27 | From 8.00am on first day until 6.00pm on final day | Utility works | Emergency Utility Works | Stanley | 124
Thames Water | Cheniston Gardens | Jnc Wrights Lane | Road Closed with local diversion | 2025-11-16 | 2025-11-21 | From 8.00am on first day until 6.00pm on final day | Utility works | Emergency Utility Works | Abingdon | 125
Thames Water | Onslow Gardens | Jnc Old Brompton Road | Road Closed with local diversion | 2025-11-16 | 2025-11-21 | From 8.00am on first day until 6.00pm on final day | Utility works | Emergency Utility Works | Courtfield | 126
OCU Group for BT | Kensington High Street | Hornton Street to Kensington Church Street | Eastbound Directional Road closed with local diversion | 2025-11-16 | Backup date 23/11/25 | From 8.00am until 10.00pm | Utility works |  | Holland | 127
Thames Water | Launceston Place | 3 | Road Closed with local diversion | 18-19/11/25 | Backup Dates 24-25/11/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 128
Thames Water | Cadogan Square | 59 | Road Closed with local diversion | 20-21/11/25 | Backup Dates 23-24/11/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 129
Kelly Traffic Management for Virgin Media | Kensington Church Street | Dukes Lane to O/s 39 | Footway Closed with local diversion | 2025-11-24 | 2025-11-26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 130
M Group for Thames Water | Kensington High Street | Kensington Church Street | Prohibited Right Hand Turn with local diversion | 24-27/11/25 | Backup Dates 12-15/01/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 131
Vital Energi | Dulford Street | Clarendon Road to Walmer Street | Road Closed with local diversion | 2025-11-24 | 2026-02-09 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Notting Dale | 132
M Group for Thames Water | Kynance Mews | 10 | Road Closed with local diversion | 24-27/11/25 | Backup dates 01-04/12/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 133
Cadent Gas | Aubrey Walk | 22 | Road Closed with local diversion | 2025-11-30 | 2025-12-05 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 134
Thames Water | Carlyle Square | 7 | Road Closed with local diversion | 2025-12-01 | 2025-12-05 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Stanley | 135
Lanes Group PLC for Thames Water | Stadium Street | Whole Street | Road Closed with local diversion | 2026-01-05 | 2026-01-06 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Chelsea Riverside | 136
M Group for Thames Water | Pavilion Road | 49 | Road Closed with local diversion | 05-09/01/26 | 0Backup date 12-16/01/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Chelsea Riverside | 137
Thames Water | Barlby Road | O/s Ladbroke Hall | Road Closed with local diversion | 12-19/01/26 | Backup Dates 26/01/26 to 02/02/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Dalgarno | 138
Cadent Gas | Pavilion Road | 120 | Road Closed with local diversion | 2026-01-26 | 2026-01-29 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 139
Cadent Gas | Ashburn Place | Jnc Cromwell Road | Road Closed with local diversion | 2026-02-02 | 2026-02-06 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Courtfield | 140
Kelly Traffic Management for Virgin Media | Duchess of Bedford's Walk | O/s Sheldrake Place | Road Closed with local diversion | 2026-02-23 | 2026-02-24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 141
M Group for Thames Water | Mossop Street | Ives Street to First Street | Road Closed with local diversion | 23-27/02/26 | Backup Dates 02-06/03/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 142
M Group for Thames Water | Aubrey Walk | Opp 8 | Road Closed with local diversion | TBA | TBA | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 143
JSM Group Limited | Kensal Road | Ladbroke Grove | Road Closed with local diversion | TBA | TBA | From 8.00am on first day until 6.00pm on final day | Utility works |  | Golborne | 144
|  |  |  | DEVELOPMENTS | [5 empty] | 145
Neilcott Construction Ltd | Pelham Street | 40 | Footway Closure | 2025-08-18 | 2025-12-24 | Weekdays From 8.00am until 5.00pm | Developer works |  | Brompton and Hans Town | 146
Ant Yapi Uk | Earl's Court Road | 24, S/o Holland Park Gate | Footway Closure | 2025-09-29 | 2027-03-26 | Weekdays From 8.00am until 5.00pm | Developer works | Footway to be used as a loading Area | Abingdon | 147
Midgard City Limited | Newcombe Street | Junction of Kensington Place | Road Closure | 2025-08-27 | 2027-03-18 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Campden | 148
FM Conway | Horton Street | Pitt Street to Holland Street | Road Closure | 2025-12-08 | 2025-12-19 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Campden | 149
Neilcott Construction Ltd | Pelham Street | Brompton Road to Old Brompton Road | Westbourne Directional Road Closure | 2024-09-16 | 2026-02-09 | Weekdays From 8.00am on first day until 5.00pm on final day | Developer works |  | Brompton and Hans Town | 150
Fenton Civil Engineering | St Albans Grove | Stanford Road to Victoria Road | Road Closed with local diversion | 2025-12-18 | 2025-12-19 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 151
|  |  |  | MOBILE LIFTING OPERATIONS | [5 empty] | 152
J &G Traffic Limited | Walton Street | Brompton Road to First Street | Road closed with local diversion | 03-04/11/25 | 07-08/01/26 | From 8.00pm to 5.00am | Mobile Lifting Operation | Nightworks | Brompton and Hans Town | 153
MK Illuminations UK Limited | Sloane Street | Sloane Square | Road Width Reduced | 2025-11-10 | 2025-11-30 | From 10.00pm until 6.00am | Mobile Lifting Operation | Nightworks | Various Wards | 154
Structural Glass Design | The Boltons | 24 | Road closed with local diversion | 2025-11-17 | Backup Date 24/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 155
Nationwide Traffic Solutions Limited | Pembridge Villas | 2 | Road Width Reduced | 2025-11-17 | Backup date 20/11/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Pembridge | 156
Thomann-Hanry Limited | Elvaston Place | S/o Citadines Hotel, Gloucester Road | Road Width Reduced | 2025-11-17 | Backup date 21/11/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Queen's Gate | 157
Chelci Group | Sloane Street | 203 | Road Width Reduced | 2025-11-19 | 2025-11-20 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 158
Chevron TM | Cathcart Road | O/s Cathcart House | Road closed with local diversion | 2025-11-19 | Backup Date 20/11/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 159
City Lifting Limited | The Boltons | 9 | Road closed with local diversion | 2025-11-19 | Backup Date 20/11/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 160
Geia Euro cargo GmbH | Manresa Road | O/s Lightfoot Hall | Road Width Reduced | 2025-11-22 | 2025-11-22 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Stanley | 161
Trust in Safe Hands Limited | St John's Gardens | 1 | Road Width Reduced | 2025-11-23 | 2025-11-23 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norlands | 162
Fitzgerald Builders Limited | Cranley Gardens | 17 to 33 | Road Width Reduced | 2025-11-23 | 2025-11-23 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Courtfield | 163
Riglift UK Limited | Elystan Place | O/s Ranelagh House | Road closed with local diversion | 2025-11-23 | Backup Date 30/11/25 | From 9.00am to 6.00pm | Mobile Lifting Operation |  | Royal Hospital | 164
Altman James Limited | The Glebe | 36 | Road closed with local diversion | 2025-11-24 | 2025-11-24 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Chelsea Riverside | 165
Lift Assist Limited | Holland Villas Road | 11 | Road closed with local diversion | 24-25/11/25 | Backup Date 01-02/12/25 | From 8.00am to 5.00pm | Mobile Lifting Operation |  | Holland | 166
Fortis Heavy Lift Group | Chelsea Manor Gardens | O/s Chelsea Towers | Road Width Reduced | 2025-11-26 | 2025-11-26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Royal Hospital | 167
J &G Traffic Limited | The Little Boltons | 6 | Road closed with local diversion | 26-27/11/25 | Backup Dates 03-04/12/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 168
Easy Shipping Limited | Oakwood Court | 129 | Road Width Reduced | 2025-11-27 | 2025-11-27 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Holland | 169
Decorative Illuminations Limited | Notting Hill Gate | O/s Mc Donalds | Road Width Reduced | 2025-11-27 | 2025-11-28 | From 8.00am to 6.00pm | Mobile Lifting Operation | Setting up a Christmas Tree | Pembridge | 170
J &G Traffic Limited | Kensington High Street | 261 | Road Width Reduced | 2025-11-27 | Backup Date 04/12/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 171
Fixer CMG Limited | Bassett Road | Whole Road | Road closed with local diversion | 2025-11-27 | 2025-11-28 | From 6.00am to 11.00pm | Mobile Lifting Operation |  | St Helens | 172
3 D Eye Limited | Hans Crescent | O/s Harrods | Road Width Reduced | 2025-11-28 | 2025-11-30 | From 10.00pm until 6.00am | Mobile Lifting Operation | Nightworks | Brompton and Hans Town | 173
PG Platforms Limited | Kensington High Street | 26 to 40 | Road Width Reduced | 2025-11-30 | 2025-11-30 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Campden | 174
PG Platforms Limited | Old Court Place | Jnc Kensington High Street | Road Width Reduced | 2025-11-30 | 2025-11-30 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Campden | 175
L & N Platforms Limited | Derry Street | S/o 99-12 Kensington High Street | Road Width Reduced | 2025-12-01 | 2025-12-01 | From 7.00pm until 11.00pm | Mobile Lifting Operation | Nightworks | Queen's Gate | 176
City Lifting Limited | The Boltons | 15 | Road closed with local diversion | 2025-12-08 | Backup Date 10/12/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 177
J &G Traffic Limited | Douro Place | 14 | Road closed with local diversion | 08-11/12/25 | Backup Dates 15-18/12/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Queen's Gate | 178
City Lifting Limited | Sydney Street | O/s Royal Brompton Hospital | Road Width Reduced | 2025-12-10 | Backup Date 11/12/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Stanley | 179
J &G Traffic Limited | Kensington High Street | O/s 261 | Road Width Reduced | 2025-12-10 | Backup Date 17/12/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 180
Costain for TfL | Malton Road | O/s Ambulance Station to Jnc Malton Mews | Road Width Reduced | 2025-12-11 | 2025-12-17 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | St Helens | 181
Lift Assist Limited | Adam and Eve Mews | O/s Army Reserve Centre | Road Width Reduced | 2025-12-11 | Backup Date 07/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 182
Wallglaze Fixing Limited | Shawfield Street | O/s Shawfield House | Road closed with local diversion | 2025-12-16 | 2025-12-16 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Royal Hospital | 183
Lift Assist Limited | Earl's Court Square | 35 to 37 | Road Width Reduced | 2025-12-17 | Backup date 13/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Earl's Court | 184
Assured Traffic Solutions | Sydney Street | Jnc King's Road | Road closed with local diversion | 2026-01-04 | Backup Date 11/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Stanley | 185
Chevron Traffic Management | Beauchamp Place | Whole Road | Road closed with local diversion | 2026-01-05 | 2026-01-06 | From 11.00pm until 6.00am | Mobile Lifting Operation | Nightworks | Brompton and Hans Town | 186
Lift Assist Limited | Godfrey Street | 37 | Road Width Reduced | 2026-01-09 | Backup Date 23/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Stanley | 187
Heathrow Cranes Limited | Earl's Court Road | Kensington High Street to Pater Street | Road closed with local diversion | 10-11/01/26 | Backup Dates 17-18/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 188
Lift Assist Limited | Queens Gate Mews | 8 | Road Width Reduced | 2026-01-12 | Backup Date 26/01/26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Queen's Gate | 189
City Lifting Limited | The Boltons | O/S 5 | Road closed with local diversion | 2026-01-21 | Backup Date 28/01/26 | From 6.30am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 190
Falcon Tower Crane Services Limited | Allen Street | O/s Avon House | Road closed with local diversion | 24-25/01/26 | Backup Dates 31/01/26 and 01/02/26 | From 6.30am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 191
Marjen Limited on behalf of Waldon Telecoms | Lancaster Road | Ladbroke Grove to 87 Lancaster Road | Road closed with local diversion | TBC | TBC | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Colville | 192
|  |  |  | LOCAL RESIDENTS - STREET PARTIES & SPECIAL EVENTS | [5 empty] | 193
RBKC | Portobello Road | Colville Terrace to Oxford Gardens | Road Closed for a Street Market | 2025-06-22 | 2025-12-21 | Closed on Sundays From 8.00am until 5.00pm | Road Closed for a Street Market | Closed on Sundays | Colville and Golborne | 194
Run Italy | Kensington High Street, Abbotsbury Road Holland Park, Ilchester Place | Various Road Closures and an eastbound directional road closure of Kensington High Street. | Various Road Closures and an eastbound directional road closure of Kensington High Street. | 2025-11-23 | 2025-11-23 | From 07.30am until 10.30am | Roads Closed for a Fun Run | Fun Run | Campden and Holland | 195
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-25 | 2025-11-25 | From 6.30pm until 11.00pm | Chelsea V FC Barcelona | Large amount of Pedestrians going to a football match | Various Wards | 196
Chelsea Physic Gardens | Royal Hospital Road | O/s Chelsea Physic Gardens | Parking Bays suspended for a charity event | 2025-11-26 | 2025-11-26 | From 8.30am until 6.00pm | Charity Event |  | Royal Hospital | 197
RBKC | Phillimore Walk | Hornton Street to Campden Hill Road | Road Closed for a Street Market | 2025-11-29 | 2025-11-29 | From 7.30am until 7.30pm | Road Closed for a Street Market |  | Campden | 198
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-30 | 2025-11-30 | Between 3.00pm and 7.00pm | Chelsea V Arsenal | Large amount of Pedestrians going to a football match | Various Wards | 199
Restart Lives | Lennox Gardens | S/o St Columba's Church | Road Closed for a Charity Event | 05-06/12/25 | Backup dates 09-10/12/25 | From 6.00pm until 7.00am | Charity Event | Road Closed Overnight to stage this event | Brompton and Hans Town | 200
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-10 | 2025-12-10 | Between 6.30pm and 11.00pm | Chelsea Women V AS Rome | Large amount of Pedestrians going to a football match | Various Wards | 201
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-13 | 2025-12-13 | Between 12.30pm and 5.00pm | Chelsea V Everton | Large amount of Pedestrians going to a football match | Various Wards | 202
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-27 | 2025-12-27 | Between 12.30pm and 5.00pm | Chelsea V Aston Villa | Large amount of Pedestrians going to a football match | Various Wards | 203
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-30 | 2025-12-30 | Between 18.00pm and 11.00pm | Chelsea V Bournemouth | Large amount of Pedestrians going to a football match | Various Wards | 204
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-17 | 2026-01-17 | Between 12.30pm and 5.00pm | Chelsea V Brentford | Large amount of Pedestrians going to a football match | Various Wards | 205
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-21 | 2026-01-21 | From 6.30pm until 11.00pm | Chelsea V Pafos FC | Large amount of Pedestrians going to a football match | Various Wards | 206
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-25 | 2026-01-25 | Between 11.00am and 3.00pm | Chelsea Women V Arsenal | Large amount of Pedestrians going to a football match | Various Wards | 207
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-31 | 2026-01-31 | Between 4.00pm and 9.00pm | Chelsea V West Ham United | Large amount of Pedestrians going to a football match | Various Wards | 208
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-02-11 | 2026-02-11 | Between 18.00pm and 11.00pm | Chelsea V Leeds United | Large amount of Pedestrians going to a football match | Various Wards | 209
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-02-21 | 2026-02-21 | Between 12.30pm and 5.00pm | Chelsea V Burnley | Large amount of Pedestrians going to a football match | Various Wards | 210
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-03-14 | 2026-03-14 | Between 12.30pm and 5.00pm | Chelsea V Newcastle United | Large amount of Pedestrians going to a football match | Various Wards | 211
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-04-11 | 2026-04-11 | Between 12.30pm and 5.00pm | Chelsea V Manchester City | Large amount of Pedestrians going to a football match | Various Wards | 212
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-04-18 | 2026-04-18 | Between 12.30pm and 5.00pm | Chelsea V Manchester United | Large amount of Pedestrians going to a football match | Various Wards | 213
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-02 | 2026-05-02 | Between 12.30pm and 5.00pm | Chelsea V Nottingham Forest | Large amount of Pedestrians going to a football match | Various Wards | 214
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-16 | 2026-05-16 | Between 12.30pm and 5.00pm | Chelsea Women V Manchester United | Large amount of Pedestrians going to a football match | Various Wards | 215
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-17 | 2026-05-17 | Between 12.30pm and 5.00pm | Chelsea V Tottenham Hotspur | Large amount of Pedestrians going to a football match | Various Wards | 216
|  |  |  | LOCAL ACTIVITIES ON THE TFL, HAMMERSMITH & FULHAM, WESTMINSTER OR BRENT NETWORKS | [5 empty] | 217
TfL | Knightsbridge | Piccadilly Underpass | Eastbound Directional Road Closure | 21-24/11/25 | 21-24/11/25 | From 8.00pm on the first day until 05.00am on the final day | Maintenance Works |  | Westminster | 218
Cadent Gas | North Pole Road | Junction of Scrubs lane to Du Cane Road | Southbound Directional Road Closure with diversion | 2025-11-10 | 2025-12-22 | From 8.00am on first day until 6.00pm on final day | Utility works | Expect Long Traffic Delays in the Area | LBH&F | 219
Olympia Development | Hammersmith Road | O/s Olympia | 3 way lights | 2025-11-16 | Backup Date 23/11/25 | From 1.00pm until 10.00pm | Crane Works | 3 way lights | LBH&F | 220
UKPN | Redcliffe Gardens | 110 | Footway Closed with a lane closure | 2025-11-22 | 2025-11-23 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Redcliffe | 221
UKPN | Redcliffe Gardens | Jnc Redcliffe Place | Footway Closed with a lane closure | 2025-11-24 | 2025-11-26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Redcliffe | 222
TfL | Chelsea Embankment | Royal Hospital Road | 3 way lights | 2025-11-27 | 2025-11-27 | From 8.00pm until 11.59pm | Traffic Signal Works |  | Royal Hospital | 223
TfL | Holland Road | Junction of Holland Gardens | Lane Closure | 2025-11-29 | 2025-11-30 | From 8.00am on first day until 4.30pm on final day | Utility works |  | Holland | 224
The Royal Albert Hall | Kensington Gore | Prince Consort Road, Bremner Road, Jay Mews | Roads Closed for an event | 2025-11-30 | 2025-12-01 | From 12.00pm on the first day until 11.59pm on the last day | Fashion Awards |  | Westminster | 225
Cadent Gas | Wood Lane | North Pole Road to Du Cane Road | Southbound Directional Road Closed with local diversion | 2025-11-30 | 2025-12-21 | From 8.00am on first day until 6.00pm on final day | Utility works |  | LBH&F | 226
Thames Water | Brompton Road | Jnc Beauchamp Place | Westbound lanes 2 and 3 closed | 2025-12-14 | 2025-12-15 | From 11.00pm until 5.00am each Night | Utility works | Nightworks | Brompton and Hans Town | 227
Westminster | Knightsbridge | Trevor Road to Brompton road | Eastbound Directional Road Closure | 2026-01-06 | 2026-01-07 | From 10.00pm until 6.00am | Resurfacing Works |  | Westminster | 228
Costain for TfL | A40 Westway | Westway Roundabout | Eastbound Weekend Closures | 2026-01-09 | 2026-03-23 | From 10.00pm on Friday night until 5.00am on the Monday Morning | Bridge Maintenance Works |  | Notting Dale | 229
Costain for TfL | A40 Westway | Marylebone Flyover | Eastbound Weekend Closures | 2026-01-19 | 2026-03-13 | Various Weekend and some weeknight closures | Bridge Maintenance Works |  | Westminster | 230
Costain for TfL | A40 Westway | Marylebone Flyover | Full A40 Closure | 2026-03-27 | 2026-04-29 | Various Weekend and some weeknight closures | Bridge Maintenance Works |  | Westminster | 231
Costain for TfL | A40 Westway | Marylebone Flyover | Westbound Weekend Closures | 2026-04-29 | 2026-05-28 | Various Weekend and some weeknight closures | Bridge Maintenance Works |  | Westminster | 232
Costain for TfL | A40 Westway | Westway Roundabout | Westbound Weekend Closures | 2026-03-27 | 2026-06-22 | From 10.00pm on Friday night until 5.00am on the Monday Morning (Excluding Bank Holiday Weekends) | Bridge Maintenance Works |  | Notting Dale | 233
Costain for TfL | Harrow Road | Edgware Road | Nighttime Road Closures | TBA | TBA | From 10.00pm until 5.00am | Resurfacing Works |  | Westminster | 234
This list is not an exhaustive list of all works that are being carried out across the Borough.
For full details of all works being carried out in the borough please use the London Works facility using the following link:
http://one.network