## Sheet1
Royal Borough of Kensington and Chelsea Works and Events Bulletin - 10th April 2024
Works Originator | Road | Location | Effect | From Date | To Date | Time | Reason | Comment | Council Ward | Line Number
. | . | . | RBKC Footway Work |  | . | . | . | . | . | 3
Royal Borough of Kensington and Chelsea | Egerton Gardens | 17 to 77 | Footway Closed with local diversion | 2024-03-25 | 2024-06-25 | From 8.00am to 5.00pm | Footway improvement works |  | Brompton and Hans Town | 4
Royal Borough of Kensington and Chelsea | Old Brompton Road | Gledhow Gardens to Bolton Gardens | Footway Closed with local diversion | 02/04/2024 | 2024-05-28 | From 8.00am to 5.00pm | Footway improvement works |  | Redcliffe | 5
Royal Borough of Kensington and Chelsea | St Charles Square | 2 to 26 | Footway Closed with local diversion | 02/04/2024 | 2024-05-08 | From 8.00am to 5.00pm | Footway improvement works |  | St Helen's | 6
Royal Borough of Kensington and Chelsea | St Charles Square | Ladbroke Grove to St Charles Place both sides | Footway Closed with local diversion | 02/04/2024 | 2024-05-08 | From 8.00am to 5.00pm | Footway improvement works |  | St Helen's | 7
Royal Borough of Kensington and Chelsea | Bosworth Road | Appleford Road to Hazelwood Crescent | Footway Closed with local diversion | 2024-04-08 | 2024-05-03 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 8
Royal Borough of Kensington and Chelsea | East Row (EFW) | Conlan Street to Southern Row | Footway Closed with local diversion | 2024-04-15 | 2024-07-05 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 9
Royal Borough of Kensington and Chelsea | Portobello Road (EFW) | Telford Road to Faraday Road + Golborne to Bonchurch Road | Footway Closed with local diversion | 2024-04-02 | 2024-05-08 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 10
Royal Borough of Kensington and Chelsea | Wornington Road (NFW) | Golborne Road to Faraday Road | Footway Closed with local diversion | 2024-04-02 | 2024-05-08 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 11
Royal Borough of Kensington and Chelsea | St Charles Square | 19 - 29 + 31 - 47 + 63 - 67 + St Charles Place | Footway Closed with local diversion | 2024-04-02 | 2024-05-08 | From 8.00am to 5.00pm | Footway improvement works |  | St Helen's | 12
| . |  | RBKC WEEKDAY RESURFACING |  | . | . | . | . | . | 13
Royal Borough of Kensington and Chelsea | Beaufort Street | 20m North of King's Rd to half way between Chelsea Pk Gdns & number 102 to 110 | Road Closure | 2024-04-16 | 2024-04-16 | From 8pm to 5am | Road Resurfacing | Night Works | Stanley | 14
Royal Borough of Kensington and Chelsea | Fulham Road | Junction with Beaufort Street | Road Closure | 2024-04-17 | 2024-04-17 | From 8pm to 5am | Road Resurfacing | Night Works | Stanley | 15
Royal Borough of Kensington and Chelsea | Fulham Road | 1 Elm Park Gdns to 101 Elm Park Gdns east bound only | Road Closure | 2024-04-17 | 2024-04-17 | From 8pm to 5am | Road Resurfacing | Night Works | Stanley | 16
Royal Borough of Kensington and Chelsea | Kensington Church Street | Holland Street to Campden Grove | Road Closure | 2024-04-18 | 2024-04-18 | From 8pm to 5am | Road Resurfacing | Night Works | Campden | 17
Royal Borough of Kensington and Chelsea | Kensington Mall | 3 to Kensington Church Street inc bend | Road Closure | 2024-04-19 | 2024-04-19 | From 8pm to 5am | Road Resurfacing | Night Works | Campden | 18
Royal Borough of Kensington and Chelsea | Kensington High Street | Addison Road to 294 east bound | Road Closure | 2024-04-29 | 2024-04-29 | From 8pm to 5am | Road Resurfacing | Night Works | Holland | 19
Royal Borough of Kensington and Chelsea | Kensington High Street | Opposite Melbury Road to opposite 292 | Road Closure | 2024-04-30 | 2024-04-30 | From 8pm to 5am | Road Resurfacing | Night Works | Abingdon | 20
Royal Borough of Kensington and Chelsea | Kensington High Street | Junction with Campden Hill Road - Hornton Street | Road Closure | 2024-05-02 | 2024-05-02 | From 8pm to 5am | Road Resurfacing | Night Works | Campden | 21
Royal Borough of Kensington and Chelsea | Holland Park Avenue | 60 to Ladbroke Grove | Road Closure | 2024-05-13 | 2024-05-13 | From 8pm to 5am | Road Resurfacing | Night Works | Pembridge | 22
Royal Borough of Kensington and Chelsea | Holland Park Avenue | 182 borough boundary to Opp Hilton exit | Road Closure | 2024-05-14 | 2024-05-14 | From 8pm to 5am | Road Resurfacing | Night Works | Norland | 23
Royal Borough of Kensington and Chelsea | Kensington High Street | Borough Boundary to 20m past Russell Road east bound | Road Closure | 2024-05-15 | 2024-05-15 | From 8pm to 5am | Road Resurfacing | Night Works | Holland | 24
Royal Borough of Kensington and Chelsea | Kensington High Street | Banham's to Earls Court Road w/bound | Road Closure | 2024-05-16 | 2024-05-16 | From 8pm to 5am | Road Resurfacing | Night Works | Abingdon | 25
Royal Borough of Kensington and Chelsea | Kensington High Street | M&S to Number 137 | Road Closure | 2024-05-17 | 2024-05-17 | From 8pm to 5am | Road Resurfacing | Night Works | Abingdon | 26
Royal Borough of Kensington and Chelsea | King's Road | Thorndyke Close east exit to Worlds End Health Centre west bound only | Directional Road Closure | 2024-05-29 | 2024-05-29 | From 8pm to 5am | Road Resurfacing | Night Works | Chelsea Riverside | 27
Royal Borough of Kensington and Chelsea | Kensington High Street | 45 including Crossing to Opp Kensington Church Street | Road Closure | 2024-05-30 | 2024-05-30 | From 8pm to 5am | Road Resurfacing | Night Works | Queen's Gate | 28
Royal Borough of Kensington and Chelsea | Ladbroke Grove | Kensal Road to Road to Bridge + Other Side of Bridge to Round About/Barlby Road | Road Closure | 2024-06-03 | 2024-06-04 | From 8pm to 5am | Road Resurfacing | Night Works | Golborne | 29
Royal Borough of Kensington and Chelsea | Ladbroke Grove | Holland Park Avenue to Ladbroke Walk | Road Closure | 2024-06-05 | 2024-06-05 | From 8pm to 5am | Road Resurfacing | Night Works | Norland and Pembridge | 30
Royal Borough of Kensington and Chelsea | Holland Park Avenue | Hillsleigh Road to West arm of Campden Hill Square | Road Closure | 2024-07-01 | 2024-07-01 | From 8pm to 5am | Road Resurfacing | Night Works | Campden | 31
. | . |  | RBKC WEEKEND RESURFACING |  | . | . | . | . | . | 32
33
. | . | . | RBKC DRAINAGE WORKS |  | . | . | . | . | . | 34
Royal Borough of Kensington and Chelsea | Ladbroke Square | Opposite 23 | Road Width Reduced | 09/04/24 | 15/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | Pembridge | 35
Royal Borough of Kensington and Chelsea | St Charles Square | Opposite 41 | Road Width Reduced | 11/04/24 | 17/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | Dalgarno | 36
Royal Borough of Kensington and Chelsea | Highlever Road | 165 | Road Width Reduced | 15/04/24 | 19/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | St Helen's | 37
Royal Borough of Kensington and Chelsea | Kensington High Street | 23 | Road Width Reduced | 15/04/24 | 18/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | Holland | 38
Royal Borough of Kensington and Chelsea | Westbourne Park Road | Side of 216 Portobello Road | Road Width Reduced | 17/04/24 | 19/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | Colville | 39
Royal Borough of Kensington and Chelsea | Telford Road | 12 | Road Width Reduced | 17/04/24 | 19/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | Golborne | 40
Royal Borough of Kensington and Chelsea | Fulham Road | 320-333 | 2 Way Lights | 22/04/24 | 26/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | Redcliffe | 41
Royal Borough of Kensington and Chelsea | Royal Hospital Road | 65 | Road Width Reduced | 24/04/24 | 27/04/24 | From 8.00 am to 5.00pm | Gully repair works |  | Royal Hospital | 42
Royal Borough of Kensington and Chelsea | Longridge Road | S/o 160 Earls Court Road | Road Width Reduced | 25/04/24 | 03/05/24 | From 8.00 am to 5.00pm | Gully repair works |  | Earl's Court | 43
Royal Borough of Kensington and Chelsea | Colville Gardens | Opposite 41 | Road Width Reduced | 25/04/24 | 01/05/24 | From 8.00 am to 5.00pm | Gully repair works |  | Colville | 44
Royal Borough of Kensington and Chelsea | Courtfield Gardens | Opposite No 5 | Road Width Reduced | 29/04/24 | 03/05/24 | From 8.00 am to 5.00pm | Gully repair works |  | Courtfield | 45
. | . |  | RBKC SPECIAL ENGINEERING PROJECTS |  | . | . | . | . | . | 46
Royal Borough of Kensington and Chelsea | Pembroke Road | Warwick Road | Eastbound directional Road Closure, plus short duration traffic holds | 27/11/23 | Summer 24 | Between 00.01am on first day until 6.00pm on final day. | Depot Works |  | Abingdon | 47
Royal Borough of Kensington and Chelsea | Sloane Street | Sloane Square to Knightsbridge | Southbound directional Road Closures Carriageway and footway width reduced Parking Suspensions | 09/01/23 | Winter 24 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | For more information on this project visit; https://sloanestreetfuture.co.uk/ | Royal Hospital and Brompton and Hans Town | 48
Royal Borough of Kensington and Chelsea | Basil Street | Junction with Sloane Street and Pavillion Road | Road Closures Carriageway width reduced/Footway width reduced/Parking Suspensions | 22/01/24 | 31/05/24 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement works | Royal Hospital and Brompton and Hans Town | 49
Royal Borough of Kensington and Chelsea | Hollywood Road | Between Fawcett Street and Cathcart Road | Road Closures Carriageway and footway width reduced Parking Suspensions | 2023-11-23 | 2024-06-03 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement works | Redcliffe | 50
Royal Borough of Kensington and Chelsea | Draycott Avenue | Junctions with Donne Place and Walton Street | Road Closures Carriageway and footway width reduced Parking Suspensions | 2024-03-01 | TBA | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement works | Brompton and Hans Town | 51
Royal Borough of Kensington and Chelsea | Pembroke Road | Warwick Road to Warwick Gardens | Road Closed local diversions | 2024-04-22 | 2024-05-18 | Between 00.01am on first day until 6.00pm on final day. | Depot Works |  | Abingdon | 52
Royal Borough of Kensington and Chelsea | Albert Bridge | Whole Bridge | Bus lane closed | 28/05/24 | 31/05/24 | Between 8.00am on first day until 6.00pm on final day. | Bridge Maintenance Works | Essential maintenance | Royal Hospital and Brompton and Hans Town | 53
Royal Borough of Kensington and Chelsea | Gloucester Road | Junction with Stanhope Gardens and A4 Cromwell Road | Road Closures Carriageway and footway width reduced Parking Suspensions | 2024-06-01 | TBA | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement works | Brompton and Hans Town/Royal Hospital and Stanley | 54
. | . | . | UTILITY COMPANY WORKS |  | . | . | . | . | . | 55
The Clancy Group for Thames Water | Ixworth Place | Jnc Sloane Avenue | Eastbound Directional Road Closed with local diversion | 2024-02-05 | 2024-04-05 | From 8.00am on first day until 6.00pm on final day | Utility works | Collapsed Sewer Repairs | Brompton and Hans Town | 56
The Clancy Group for Thames Water | Fernshaw Road | 4 to 6 | Road Closed with local diversion | 2024-03-14 | 2024-04-11 | From 8.00am on first day until 6.00pm on final day | Utility works | Collapsed Sewer Repairs | Stanley | 57
The Clancy Group for Thames Water | Elgin Crescent | 30 | Road Closed with local diversion | 2024-03-14 | 2024-04-11 | From 8.00am on first day until 6.00pm on final day | Utility works | Collapsed Sewer Repairs | Colville | 58
Cappagh / Thames Water | Westbourne Grove | 192 | Road Closed with local diversion | 2024-04-02 | 2024-04-23 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Colville | 59
GTM for UKPN | Pelham Street | Brompton Road to Pelham Place | Westbound Directional Road Closure | 02-19/04/24 | Backup dates 09-26/04/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 60
Morrison Water Services / Thames Water | Earl's Court Road | 94 | Road Closed with local diversion | 03-05/04/24 | Backup Dates 08-10/04/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Abingdon | 61
Cadent Gas | Smith Street | 50, Jnc King's Road | Road Closed with local diversion | 2024-04-08 | 2024-04-12 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Royal Hospital | 62
Thames Water | Ladbroke Grove | Jnc Harrow Road | Southbound Directional Road Closed with local diversion | 2024-04-08 | 2024-04-12 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Golborne | 63
Keltic Traffic Management for Cadent Gas | Glebe Place | Jnc King's Road | Road Closed with local diversion | 2024-04-11 | 2024-04-18 | From 8.00am on first day until 6.00pm on final day | Utility works | This is to facilitate emergency Repair works on the King's Road | Chelsea Riverside | 64
Keltic Traffic Management for Cadent Gas | Manresa Road | Jnc King's Road | Road Closed with local diversion | 2024-04-11 | 2024-04-18 | From 8.00am on first day until 6.00pm on final day | Utility works | This is to facilitate emergency Repair works on the King's Road | Chelsea Riverside | 65
Morrison Water Services / Thames Water | Aubrey Walk | Jnc Hillsleigh Road | Road Closed with local diversion | 13-18/04/24 | Backup Dates 20-25/05/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 66
Morrison Water Services / Thames Water | Old Church Street | 17 | Road Closed with local diversion | 2024-04-15 | 2024-04-19 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Chelsea Riverside | 67
Sunbelt Rentals Ltd for BT Openreach | Yeomans Row | 28 | Road Closed with local diversion | 2024-04-17 | 2024-04-19 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 68
Morrison Water Services / Thames Water | Hillgate Street | 1 | Road Closed with local diversion | 2024-04-22 | Backup date 29/04/2024 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 69
Thames Water | Ansdell Street | Thackery Street | Road Closed with local diversion | 22-24/04/2024 | Backup dates 29/04/2024 to 01/05/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 70
Cappagh / Thames Water | Lower Addison Road | Jnc Holland Road | Road Closed with local diversion | 2024-04-22 | 2024-05-06 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Holland | 71
Transport for London | Stanhope Mews West | Jnc Stanhope Gardens | Directional Road Closed with local diversion | 23/04/24 to 19/06/24 | Backup dates 19/06/24 to 31/07/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Courtfield | 72
Cappagh | Talbot Road | 130 , Jnc Portobello Road | Directional Road Closed with local diversion | 2024-04-29 | 2024-05-20 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Colville | 73
Thames Water | Holbein Place | 1 | Road Closed with local diversion | 30/04/24 to 02/05/24 | Backup dates 07-09/05/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Royal Hospital | 74
Thames Water | Radnor Walk | S/o 113-115 King's Road | Road Closed with local diversion | 2024-05-20 | 2024-05-20 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Royal Hospital | 75
Thames Water / Core Highways | Egerton Gardens | Jnc Egerton Crescent | Road Closed with local diversion | 2024-05-20 | 2024-05-20 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 76
Ferns TM Limited | Elvaston Place | Jnc Queen's Gate | Directional Road Closed with local diversion | 2024-05-28 | 2024-05-30 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 77
Thames Water | Palace Gardens Terrace | 49 | Road Closed with local diversion | 28-30/05/24 | Backup dates 03-06/06/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 78
Morrison Water Services / Thames Water | Shrewsbury Street | Rootes Drive to Hillman Drive | Road Closed with local diversion | 03-09/06/24 | Backup dates 10-16/06/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Dalgarno | 79
Cappagh Contractors for Thames Water | Colville Terrace | 15 | Road Closed with local diversion | 2024-06-10 | 2024-06-28 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Colville | 80
Thames Water | Ormonde Gate | 21 | Road Closed with local diversion | 18-20/06/2024 | Backup dates 25-27/06/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Royal Hospital | 81
Morrison Water Services / Thames Water | Stratford Road | Jnc Marloes Road | Road Closed with local diversion | 01-04/07/2024 | Backup dates 15-18/07/24 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Abingdon | 82
Morrison Water Services / Thames Water | Old Brompton Road | Jnc Eardley Crescent to the Bridge | Road Closed with local diversion | 2024-07-22 | 2024-08-30 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Earl's Court | 83
. | . | . | DEVELOPMENTS |  | . | . | . | . | . | 84
Edgewater Contracts and Specialist Joinery Limited | Templeton Place | O/s K&K Hotel | Footway Closed | 2024-01-08 | 2024-10-31 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Earl's Court | 85
Underhouse Management Limited | Mossop Street | S/o 47 Denyer Street | Footway Closed | 2024-02-26 | 2024-07-31 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Brompton and Hans Town | 86
Morgan Sindall Construction and Infrastructure Limited | Acklam Road | O/s The Al Manaar Muslim Cultural and Infrastructure Limited | Road Closed with local diversion | 2024-02-29 | 2024-06-28 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Golborne | 87
Metro Traffic Management for Clarke Facades | Ashburn Place | From Cromwell Road to Courtfield Road | Footway Closed with local diversion | 15/04/2024 to 27/05/24 | Backup dates 22/04/24 to 03/06/24 | From 8.00am on first day until 6.00pm on final day | Developer works | Western footway closure | Golborne | 88
. | . |  | MOBILE LIFTING OPERATIONS |  | . | . | . | . | . | 89
Marjen Ltd for Waldon Telecoms | Kensington High Street | O/s Hilton London Olympia Hotel | Eastbound Directional Road Closure with Major Diversion | 2024-03-24 | Backup date 14/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Holland | 90
Nationwide Traffic Solutions | The Little Boltons | 27 | Road Closed with local diversion | 2024-04-03 | Backup date 17/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 91
Nationwide Traffic Solutions | Chelsea Manor Gardens | Whole Road | Road Closed with local diversion | 06/04/24 | Backup Date 13/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Royal Hospital | 92
Marjen Ltd for Waldon Telecoms | Kensington High Street | O/s Hilton London Olympia Hotel | Eastbound Directional Road Closure with Major Diversion | 2024-04-07 | Backup dates 21 & 28/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Holland | 93
Nationwide Traffic Solutions | Queen's Gate Gardens | 26 to 27 | Road Closed with local diversion | 2024-04-09 | Backup date 17/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Queen's Gate | 94
Size Group | St John's Gardens | 1 | Road Width Reduced | 2024-04-10 | 2024-04-12 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 95
LTS Traffic Management Limited | Appleford Road | 36 | Road Width Reduced | 2024-04-10 | Backup date 17/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Golborne | 96
Lift Assist Limited | Cathcart Road | 5 | Road Width Reduced | 2024-04-11 | 2024-04-18 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Redcliffe | 97
Marjen Ltd for Waldon Telecoms | Kensington High Street | 178 to 204 | Eastbound Directional Road Closure with Major Diversion | 2024-04-14 | Backup Date 21/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Campden | 98
Marjen Ltd for Waldon Telecoms | Phillimore Walk | O/s 30 to Jnc Phillimore Gardens | Road Closed with local diversion | 2024-04-14 | Backup Date 21/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Campden | 99
|  |  | Road Width Reduced | 2024-04-15 | 2024-04-17 | From 10.00pm to 5.00am | Mobile Lifting Operation | Night Works | Brompton and Hans Town | 100
Chevron Traffic Management | Clareville Grove | Jnc Old Brompton Road | Road Closed with local diversion | 15-24/04/24 | Backup Dates 29/04/24 to 09/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Courtfield | 101
J &G Traffic Management | Aubrey Walk | 22 | Road Closed with local diversion | 2024-04-16 | Backup Date 23/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Campden | 102
Trident Lifting Solutions Limited | Manresa Road | 21 | Road Width Reduced | 2024-04-17 | 2024-04-17 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Stanley | 103
Size Group | St John's Gardens | 1 | Road Width Reduced | 2024-04-17 | 2024-04-19 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 104
Premier Lifting & Engineering Services | Allen Street | 8 | Road Closed with local diversion | 2024-04-19 | 2024-04-19 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 105
City Lifting Limited | Pembridge Villas | R/o 133-139 Westbourne Villas | Road Closed with local diversion | 22-21/04/24 | Backup dates 27-28/04/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Pembridge | 106
City Lifting Limited | Pembridge Place | 8 | Road Closed with local diversion | 2024-04-23 | Backup date 01/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Pembridge | 107
Size Group | St John's Gardens | 1 | Road Width Reduced | 2024-04-24 | 2024-04-26 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 108
Riglift UK Limited | Basil Street | 1 to 7 Court House | Road Width Reduced | 2024-04-27 | 2024-04-27 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 109
City Lifting Limited | Earl's Court Road | Jnc Old Brompton Road | Directional Road Closed with local diversion | 2024-04-27 | Backup dates 04 + 11 + 18/05/24 | From 7.00am to 6.00pm | Crane works on the TfL Road Network | Lane Closure and Prohibited left hand turn into old Brompton Road | Earl's Court | 110
J & G Traffic Limited | Campden Hill | Holland Park Villas | Road Closed with local diversion | 2024-04-29 | Backup date 02/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Campden | 111
Chevron TM | Cromwell Place | Cromwell Road | Prohibited Right hand turn | 2024-04-30 | 2024-05-01 | From 10.00pm to 5.00am | Crane Operation on the Cromwell Road | Night works | Brompton and Hans Town | 112
City Lifting Limited | Pelham Street | 40 | Road Closed with local diversion | 2024-05-04 | Backup date 11/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 113
Lift Assist Limited | Gloucester Walk | 17 | Road Width Reduced | 2024-05-07 | Backup Date 21/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Campden | 114
Nationwide Traffic Solutions | Clabon Mews | 28 | Road Width Reduced | 2024-05-08 | Backup Date 15/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 115
Owl Films Limited | Sumner Place | Fulham Road to Onslow Square | Road Closed with local diversion | 2024-05-08 | 2024-05-08 | From 8.00am to 11.00pm | Mobile Lifting Operation |  | Courtfield | 116
City Lifting Limited | Kensington Square | 15 | Road closed with local diversion | 2024-05-12 | Backup date 19/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Queen's Gate | 117
Mitre Construction | Blackland's Terrace | S/o 68-70 King's Road | Road closed with local diversion | 2024-05-15 | 2024-05-16 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Royal Hospital | 118
Jackson River Films Limited | Acklam Road | Whole of the southern section of the road | Road closed with local diversion | 2024-05-18 | 2024-05-19 | From 08.00am on the 18/05/24 until 06.30am on the 19/05/24 | Mobile Lifting Operation | Traffic Holds | Golborne | 119
Jackson River Films Limited | Ladbroke Grove | 167 | Road closed with local diversion | 2024-05-20 | Backup date 19-20/05/24 | From Midnight to 05.30am | Mobile Lifting Operation | Traffic Holds | Notting Dale | 120
Chevron Traffic Management | Adiar Road | Jnc Appleford Road | Road closed with local diversion | 2025-05-20 | Backup date 22-23/06/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Golborne | 121
Nationwide Traffic Solutions | Dawson Place | 25 | Road closed with local diversion | 2024-05-21 | Backup date 28/05/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Pembridge | 122
Morgans Lifting Services Limited | Egerton Gardens | 2024-12-11 | Road closed with local diversion | 2024-06-11 | Backup date 18/06/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 123
Nationwide Traffic Solutions | Basil Street | O/s Harrods | Road closed with local diversion | 15-16/06/24 | Backup dates 22-23/06/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 124
J&G Traffic Limited | Campden Hill | Holland Park Villas | Road closed with local diversion | 2024-06-24 | Backup dates 01/07/24 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Holland | 125
City Lifting Limited | Lexham Gardens | 1 | Road Width Reduced | 2024-09-02 | 2024-09-04 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 126
. | . |  | LOCAL RESIDENTS - STREET PARTIES & SPECIAL EVENTS |  | . | . | . | . | . | 127
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2024-04-15 | 2024-04-15 | Between 6.00pm and 10.30pm | Chelsea V Everton | Large amount of Pedestrians going to a football match | Various Wards | 128
Rough Trade | Blenheim Crescent | Talbot Road | Large Event | 2024-04-20 | 2024-04-20 | Between 10.00am to 4.00pm | Event |  | Colville | 129
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2024-04-21 | 2024-04-21 | Between 6.30pm and 10.30pm | Chelsea Ladies V Aston Villa | Large amount of Pedestrians going to a football match | Various Wards | 130
Garden House School | Sloane Terrace | O/s Cadogan Hall | Event | 2024-04-23 | 2024-04-23 | Between 9.00am to 11.00pm | Event in the Hall |  | Brompton and Hans Town | 131
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 04/05/24 | 04/05/24 | Between 1.30pm and 6.00pm | Chelsea V West Ham | Large amount of Pedestrians going to a football match | Various Wards | 132
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 19/05/24 | 19/05/24 | Between 2.30pm and 7.00pm | Chelsea V AFC Bournemouth | Large amount of Pedestrians going to a football match | Various Wards | 133
Moonwalk London | Various Road | Various Road through out the borough | Large amount of walkers on the street | 18/05/24 | 19/05/24 | Between 8.00pm until 8.00am | Charity Event | Large amount of Pedestrians walking for this event | Various Wards | 134
RHS Chelsea | Royal Hospital Road | Chelsea Bridge Road | Large amount of Pedestrians going to the Chelsea Flower Show | 2024-05-22 | 2024-05-25 | Between 8.00am to 7.00pm | Chelsea Flower Show | Large amount of Pedestrians going to the Chelsea Flower Show | Royal Hospital | 135
the Great Exhibition Road exhibition | Exhibition Road | Cromwell Road to Prince Consort Road | Road closed for a community Event | 2024-06-14 | 2024-06-16 | From 7.00am on the first day until 10.00pm on the last day | Event |  | Brompton and Hans Town | 136
Ten Acres Residents Association | Gertrude Street | Jnc Hobury Street | Road closed for a community Event | 2024-06-19 | 2024-06-19 | From 9.00am to 10.30pm | Community Event |  | Stanley | 137
. | . |  | LOCAL ACTIVITIES ON THE TFL, HAMMERSMITH & FULHAM, WESTMINSTER OR BRENT NETWORKS |  |  |  |  | . |  | 138
Thames Water | Cromwell Road | Jnc Earl's Court Road | Contra Flow | 18/01/24 | TBA | From 8.00am on the first day until 5.00pm on the last day | Water leak |  | Earl's Court | 139
Olympia | West Cromwell Road | Eastbound Directional Road Closure | North End Road to Warwick Road | 30/03/2024 to 01/04/24 | Backup dates 26-28/04/24 | From 1.00am on the first day until 10.00pm on the last day | Crane Operation | To install a crane on top of Tesco | Abingdon | 140
City Lifting Limited | Cromwell Road | Outside of the Cromwell Hospital |  | 07-08/04/24 | Backup dates 14-15 & 21-22/04/24 | From Midnight on the first day until 3.00am the next day | Crane Operation | Installing a generator to the Cromwell Hospital | Abingdon | 141
Westminster | Prince Consult Road | Kensington Gore | Road Closure | 14/04/24 | 14/04/24 | From 07.00am until 10.00pm | Event |  | Westminster | 142
Olympia | Hammersmith Road | O/s Olympia | Road Closure | 19/04/24 | 21/04/24 | From 10.00am on the first day until 8.00pm on the last day | Crane Operation |  | LBH&F | 143
Hyperoptic | Warwick Road | Opposite the Underground Station | F/w Closed C/w Walkway | 20/04/24 | 21/04/24 | From 8.00am on the first day until 4.30pm on the last day | Utility works |  | Earl's Court | 144
Thames Water | Earl's Court Road | Jnc Hogarth Road | Lane Closure | 2024-04-24 | 2024-04-26 | From 8.00am on the first day until 5.00pm on the last day | Utility works |  | Earl's Court | 145
Thames Water | Holland Road | Napier Road | Lane Closure | 2024-04-24 | 2024-04-26 | From 8.00am on the first day until 5.00pm on the last day | Utility works |  | Holland | 146
Virgin Media | Cromwell Road | 189 | Lane Closure | 2024-04-26 | 2024-04-27 | From 9.30pm to 5.00am | Utility works | Nightworks | Earl's Court | 147
City Lifting Limited | Earl's Court Road | Jnc Old Brompton Road | Directional Road Closed with local diversion | 2024-04-27 | Backup dates 04 + 11 + 18/05/24 | From 7.00am to 6.00pm | Crane works | Lane Closure and Prohibited left hand turn into old Brompton Road | Earl's Court | 148
Chevron TM | Cromwell Road | O/s Museum | Lane Closure | 30/04/24 | 02/05/24 | From 10.00pm to 5.00am | Crane Operation | Nighttime | Brompton and Hans Town | 149
Cadent Gas | Cheyne Walk | Jnc Blantyre Street | Lane Closure | 2024-05-08 | 2024-05-08 | From 8.00am to 4.00pm | Utility works |  | Chelsea Riverside | 150
Cadent Gas | Addison Crescent | Jnc Holland Road | Lane Closure | 2024-05-18 | 2024-05-18 | From 8.00am to 12.00 noon | Utility works |  | Holland | 151
Cadent Gas | Warwick Gardens | Jnc Kensington High Street | Lane Closure | 2024-05-18 | 2024-05-18 | From 8.00am to 12.00 noon | Utility works |  | Abingdon | 152
Thames Water | Knightsbridge | Jnc Albert Gate | Lane Closure | 2024-05-25 | 2024-06-11 | From 8.00am to 12.00 noon | Utility works |  | Westminster | 153
Thames Water | Cromwell Road | Queens Gate | Lane Closure | 2024-06-17 | 2024-06-18 | From 10.00pm to 5.00am | Utility works | Nighttime | Queen's Gate | 154
Westminster and TfL | Grosvenor Road | Lupus Street to Belgrave Place | Road Closed with local diversion | TBA | TBA | Sunday Closure | Westminster and TfL | Westminster and TfL | Westminster | 155
Thames Bridges Trk 2024 | Chelsea Embankment | From Bishops Park in Fulham to Lambeth | Large amount of walkers on the footway | 2024-09-14 | 2024-09-14 | 10.00am to 10..00pm | Charity walk | Chelsea Embankment between Battersea Bridge to Albert Bridge | Chelsea Riverside | 156
This list is not an exhaustive list of all works that are being carried out across the Borough.
For full details of all works being carried out in the borough please use the London Works facility using the following link:
http://one.network
Note on E2: ehetohu:

## Sheet2
Note on C1: ehetohu: