## Sheet1
Royal Borough of Kensington and Chelsea Works and Events Bulletin - 10th July 2025
Works Originator | Road | Location | Effect | From Date | To Date | Time | Reason | Comment | Council Ward | Line Number
|  |  |  | RBKC Footway Work | [5 empty] | 3
Royal Borough of Kensington and Chelsea | Oxford Gardens | Ladbroke Grove - St Marks Road | Footway Closed with local diversion | 2025-04-14 | 2025-08-05 | From 8.00am to 5.00pm | Footway improvement works |  | St Helen's | 4
Royal Borough of Kensington and Chelsea | Dalgarno Way | Delgarno Gardens to Sutton Way | Footway Closed with local diversion | 2025-04-28 | 2025-07-21 | From 8.00am to 5.00pm | Footway improvement works |  | Dalgarno | 5
Royal Borough of Kensington and Chelsea | Dalgarno Way | Sutton way to Webb Close & Lamp 0014 to 0018 Sutton Way | Footway Closed with local diversion | 2025-04-28 | 2025-07-21 | From 8.00am to 5.00pm | Footway improvement works |  | Dalgarno | 6
Royal Borough of Kensington and Chelsea | St Johns Gardens | Clarendon Road - Lansdown Road O/s 44 & Lansdowne Road to Clarendon Road | Footway Closed with local diversion | 2025-06-03 | 2025-07-16 | From 8.00am to 5.00pm | Footway improvement works |  | Norland | 7
Royal Borough of Kensington and Chelsea | Silchester Road | Bridge - Kings Down close | Footway Closed with local diversion | 2025-06-16 | 2025-07-25 | From 8.00am to 5.00pm | Footway improvement works |  | Notting Dale | 8
Royal Borough of Kensington and Chelsea | Bramley Road | Cambridge Gardens to Crowthorne Road | Footway Closed with local diversion | 2025-06-16 | 2025-07-18 | From 8.00am to 5.00pm | Footway improvement works |  | St Helen's | 9
Royal Borough of Kensington and Chelsea | Abingdon Road | Scarsdale Villas to Stratford Road | Footway Closed with local diversion | 2025-06-18 | 2025-07-25 | From 8.00am to 5.00pm | Footway improvement works |  | Abingdon | 10
Royal Borough of Kensington and Chelsea | Clarendon Road | Ladbroke Road to Lansdowne Walk plus Lansdowne Walk Clarendon Cross | Footway Closed with local diversion | 2025-06-19 | 2025-10-10 | From 8.00am to 5.00pm | Footway improvement works |  | Norland | 11
Royal Borough of Kensington and Chelsea | Cresswell Gardens | Old Brompton Road | Footway Closed with local diversion | 2025-06-23 | 2025-08-05 | From 8.00am to 5.00pm | Footway improvement works |  | Redcliffe | 12
Royal Borough of Kensington and Chelsea | Wetherby Place | Gloucester Road - Rosary Gardens and Hereford Square to Rosary Gardens | Footway Closed with local diversion | 2025-07-02 | 2025-07-22 | From 8.00am to 5.00pm | Footway improvement works |  | Courtfield | 13
Royal Borough of Kensington and Chelsea | St Helens Gardens | Oxford Gardens - Cambridge Gardens | Footway Closed with local diversion | 2025-07-09 | 2025-07-24 | From 8.00am to 5.00pm | Footway improvement works |  | St Helen's | 14
Royal Borough of Kensington and Chelsea | Abingdon Villas | Allen Street to Marloes Road | Footway Closed with local diversion | 2025-07-22 | 2025-09-22 | From 8.00am to 5.00pm | Footway improvement works |  | Abingdon | 15
Royal Borough of Kensington and Chelsea | Stadium Street | O/S 41 | Footway Closed with local diversion | 2025-07-23 | 2025-08-12 | From 8.00am to 5.00pm | Footway improvement works |  | Chelsea Riverside | 16
Royal Borough of Kensington and Chelsea | Bramley Road | Silchester Road to Whitchurch Road | Footway Closed with local diversion | 2025-07-31 | 2025-08-01 | From 8.00am to 5.00pm | Footway improvement works |  | Notting Dale | 17
Royal Borough of Kensington and Chelsea | Allen Street | Scarsdale to Stratford Road | Footway Closed with local diversion | 2025-08-26 | 2025-09-16 | From 8.00am to 5.00pm | Footway improvement works |  | Abingdon | 18
Royal Borough of Kensington and Chelsea | Elkstone Road | From s/l 010 to s/ 015 | Footway Closed with local diversion | 2025-08-28 | 2025-09-30 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 19
Royal Borough of Kensington and Chelsea | Earls Court Road | Pembroke Mews to Pembroke Square | Footway Closed with local diversion | 2025-09-01 | 2025-09-29 | From 8.00am to 5.00pm | Footway improvement works |  | Abingdon | 20
Royal Borough of Kensington and Chelsea | South Edwardes Square | Southern Leg | Footway Closed with local diversion | 2025-09-01 | 2025-11-12 | From 8.00am to 5.00pm | Footway improvement works |  | Abingdon | 21
Royal Borough of Kensington and Chelsea | King's Road | Old Church Street to Designer Guild | Footway Closed with local diversion | 2025-09-01 | 2025-09-12 | From 8.00am to 5.00pm | Footway improvement works |  | Stanley | 22
Royal Borough of Kensington and Chelsea | Ladbroke Grove | Blenheim Crescent to opposite 99 | Footway Closed with local diversion | 2025-09-01 | 2025-09-16 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 23
Royal Borough of Kensington and Chelsea | Colville Road | Westbourne Grove to Lonsdale Road | Footway Closed with local diversion | 2025-09-01 | 2025-09-29 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 24
Royal Borough of Kensington and Chelsea | Blenheim Crescent | Ladbroke Grove to Kensington Park Road | Footway Closed with local diversion | 2025-09-17 | 2025-09-25 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 25
Royal Borough of Kensington and Chelsea | Kensington Park Rd | Blenheim Crescent to Westbourne Park Road | Footway Closed with local diversion | 2025-09-17 | 2025-10-10 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 26
Royal Borough of Kensington and Chelsea | All saint's Road | Tavistock Road to Tavistock Crescent | Footway Closed with local diversion | 2025-09-18 | 2025-10-15 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 27
Royal Borough of Kensington and Chelsea | Sirdar Road | Treadgold - 27 Wilsham Street | Footway Closed with local diversion | 2025-09-22 | 2026-02-03 | From 8.00am to 5.00pm | Footway improvement works |  | Notting Dale | 28
Royal Borough of Kensington and Chelsea | Berkeley Gardens | Kensington Church St junction from no. 104 to no. 7 & no. 106 to 21b Brunswick Gardens | Footway Closed with local diversion | 2025-09-23 | 2026-10-13 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 29
Royal Borough of Kensington and Chelsea | Ladbroke Grove WFW | Cornwall Crescent to Lancaster Road | Footway Closed with local diversion | 2025-09-30 | 2025-11-24 | From 8.00am to 5.00pm | Footway improvement works |  | Abingdon | 30
Royal Borough of Kensington and Chelsea | Denbigh Road | Denbigh Terrace to Westbourne Grove | Footway Closed with local diversion | 2025-09-30 | 2025-10-28 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 31
Royal Borough of Kensington and Chelsea | Ladbroke Gardens | Ladbroke Grove to Kensington Park Road | Footway Closed with local diversion | 2025-10-01 | 2025-10-15 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 32
Royal Borough of Kensington and Chelsea | King's Road | outside 183, Outside IV Res - Oakly Street | Footway Closed with local diversion | 2025-10-13 | 2025-10-28 | From 8.00am to 5.00pm | Footway improvement works |  | Royal Hospital | 33
Royal Borough of Kensington and Chelsea | Morgan Road | Worington Road to St Ervans Road | Footway Closed with local diversion | 2025-10-13 | 2025-10-31 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 34
Royal Borough of Kensington and Chelsea | Brunswick Gardens | nos. 11 to 33 Berkely Gardens & opposite to nos. 3-7 | Footway Closed with local diversion | 2025-10-14 | 2025-11-05 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 35
Royal Borough of Kensington and Chelsea | Tavistock Crescent | Tavistock Road to St Lukes Road | Footway Closed with local diversion | 2025-10-16 | 2025-11-10 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 36
Royal Borough of Kensington and Chelsea | Oxford Gardens | St Lawrence Terrace to Portobello Road | Footway Closed with local diversion | 2025-10-29 | 2025-11-14 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 37
Royal Borough of Kensington and Chelsea | Chesterton Road | St Lawrence Terrace to Portobello Road | Footway Closed with local diversion | 2025-10-29 | 2025-12-16 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 38
Royal Borough of Kensington and Chelsea | St Lawrence Terrace | Chesterton Road junction to no.18 & at end of no. 38 Oxford Gardens to end of no. 21 | Footway Closed with local diversion | 2025-11-03 | 2025-12-12 | From 8.00am to 5.00pm | Footway improvement works |  | Golborne | 39
Royal Borough of Kensington and Chelsea | Kensington Mall | Kensington Church Street to Palace Garden Terrace | Footway Closed with local diversion | 2025-11-06 | 2025-11-14 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 40
Royal Borough of Kensington and Chelsea | Jameson Street | Kensington Place to Uxbridge Street | Footway Closed with local diversion | 2025-11-10 | 2025-12-05 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 41
Royal Borough of Kensington and Chelsea | Colville Gardens | Colville Terrace to Talbot Road | Footway Closed with local diversion | 2025-11-11 | 2025-12-03 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 42
Royal Borough of Kensington and Chelsea | Palace Gardens Terrace | O/s 82-104 and 60-64 | Footway Closed with local diversion | 2025-11-17 | 2025-12-10 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 43
Royal Borough of Kensington and Chelsea | Westbourne Park Rd | Ladbroke Grove to Kensington Park Road | Footway Closed with local diversion | 2025-11-25 | 2025-12-05 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 44
Royal Borough of Kensington and Chelsea | Colville Terrace | Colville Gardens to Powis Square | Footway Closed with local diversion | 2025-12-04 | 2025-12-15 | From 8.00am to 5.00pm | Footway improvement works |  | Colville | 45
Royal Borough of Kensington and Chelsea | Campden Hill Square | Opp. 24 to Holland Park Rd & no. 16 to Hillsleigh Road | Footway Closed with local diversion | 2026-01-05 | 2026-02-05 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 46
Royal Borough of Kensington and Chelsea | Hillsleigh Road | outside no. 17-16 + Aubrey Walk to Campden Hill Square | Footway Closed with local diversion | 2026-01-05 | 2026-02-18 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 47
Royal Borough of Kensington and Chelsea | Aubrey Walk | No. 1 to Hillsleigh Road | Footway Closed with local diversion | 2026-01-05 | 2026-02-18 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 48
Royal Borough of Kensington and Chelsea | Ladbroke Road | Ladbroke Terrace to Kensington Park Road | Footway Closed with local diversion | 2026-01-05 | 2026-02-26 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 49
Royal Borough of Kensington and Chelsea | Kensington Ch St | Kensington Mall to Notting hill Gate | Footway Closed with local diversion | 2026-01-05 | 2026-02-05 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 50
Royal Borough of Kensington and Chelsea | Aubrey Road | outside 8c to Holland Park Rd and no. 29 to Holland Park Road | Footway Closed with local diversion | 2026-02-06 | 2026-04-02 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 51
Royal Borough of Kensington and Chelsea | Notting Hill Gate | O/S 29-35 and O/S 34 - Linden Gardens | Footway Closed with local diversion | 2026-02-06 | 2026-03-05 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 52
Royal Borough of Kensington and Chelsea | Campden Hill Gardens | opp. No. 15 to Campden Hill Road | Footway Closed with local diversion | 2026-02-19 | 2026-03-12 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 53
Royal Borough of Kensington and Chelsea | Ladbroke Grove | Holland Park Avenue to Ladbroke Walk | Footway Closed with local diversion | 2026-03-06 | 2026-03-26 | From 8.00am to 5.00pm | Footway improvement works |  | Pembridge | 54
Royal Borough of Kensington and Chelsea | Campden Hill Rd | Uxbridge Road to Notting Hill Gate | Footway Closed with local diversion | 2026-03-13 | 2026-03-24 | From 8.00am to 5.00pm | Footway improvement works |  | Campden | 55
|  |  |  | RBKC WEEKDAY RESURFACING | [5 empty] | 56
Royal Borough of Kensington and Chelsea | Bramley Road | 3x Locations in folder | Road Closure | 2025-07-31 | 2025-08-01 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Notting Dale | 57
Royal Borough of Kensington and Chelsea | Chelsea Manor Street | Britten Street to Flood Walk | Road Closure | 2025-10-07 | 2025-10-07 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Royal Hospital | 58
Royal Borough of Kensington and Chelsea | Dalgarno Way | Lamp 0014 to 0018 Sutton Way (corner) - Table Top | Road Closure | 2025-12-01 | 2025-12-01 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Dalgarno | 59
Royal Borough of Kensington and Chelsea | Dalgarno Way | Dalgarno Gardens to No.6 | Road Closure | 2025-12-01 | 2025-12-01 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Dalgarno | 60
Royal Borough of Kensington and Chelsea | Lansdowne Rise | Clarendon Road - Lansdown Crescent | Road Closure | 2025-12-02 | 2025-12-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 61
Royal Borough of Kensington and Chelsea | Lansdowne Road | Lansdowne Rise - St John Gardens | Road Closure | 2025-12-02 | 2025-12-03 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 62
Royal Borough of Kensington and Chelsea | St Johns Gardens | Clarendon Road - Ladbroke Gove | Road Closure | 2025-12-04 | 2025-12-05 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Norland | 63
Royal Borough of Kensington and Chelsea | Sirdar Road | Treadgold Street - Stoneleigh Place | Road Closure | 2025-12-05 | 2025-12-05 | From 8.00am to 5.00pm | Carriageway Resurfacing |  | Notting Dale | 64
|  |  |  | RBKC NIGHT RESURFACING | [5 empty] | 65
Royal Borough of Kensington and Chelsea | Sloane Square | Sloane Street to Lower Sloane Street | Road Closure | 2025-11-03 | 2025-11-07 | From 8.00PM to 6.00AM | Carriageway Resurfacing | Night Works | Royal Hospital | 66
|  |  |  | RBKC DRAINAGE WORKS | [5 empty] | 67
Royal Borough of Kensington and Chelsea | Queensberry Mews West | 4 | Road Width Reduced | 07/0725 | 09/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Courtfield | 68
Royal Borough of Kensington and Chelsea | Phillimore Wall | Side of 2 Phillimore Gardens | Road Width Reduced | 09/07/25 | 11/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Campden | 69
Royal Borough of Kensington and Chelsea | Barkston Gardens | No 6-12 | Road Width Reduced | 10/07/25 | 16/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Earl's Court | 70
Royal Borough of Kensington and Chelsea | Earls Court Gardens | 28 | Road Width Reduced | 14/07/25 | 18/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Earl's Court | 71
Royal Borough of Kensington and Chelsea | Kenway Road | 28 | Road Width Reduced | 16/07/25 | 21/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Earl's Court | 72
Royal Borough of Kensington and Chelsea | Collingham Gardens | 47 | Road Width Reduced | 17/07/25 | 22/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Courtfield | 73
Royal Borough of Kensington and Chelsea | Kensington High Street | 207 | Lane Closure | 21/07/25 | 23/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Abingdon | 74
Royal Borough of Kensington and Chelsea | Wellington Square | 35 | Road Width Reduced | 22/07/25 | 25/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Royal Hospital | 75
Royal Borough of Kensington and Chelsea | Harrington Gardens | 75 | Road Width Reduced | 24/07/25 | 28/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Courtfield | 76
Royal Borough of Kensington and Chelsea | Pimlico Road | 1-94 Holbein House | Contraflow | 28/07/25 | 30/07/25 | From 8.00 am to 5.00pm | Gully repair works |  | Royal hospital | 77
|  |  |  | RBKC SPECIAL ENGINEERING PROJECTS | [5 empty] | 78
Royal Borough of Kensington and Chelsea | Sloane Square | Junction with Symons Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 31/03/25 | 27/10/25 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 79
Royal Borough of Kensington and Chelsea | Symons Street | Cadogan Gardens to Sloane Square | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 31/03/25 | 27/10/25 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Compound Area | Royal Hospital | 80
Royal Borough of Kensington and Chelsea | Ensor Mews | Jnc Onslow Gardens | Road Closed with local diversion | 2025-04-14 | 2025-08-22 | Between 8.00am on first day until 6.00pm on final day. | Repair works to Archway |  | Courtfield | 81
Royal Borough of Kensington and Chelsea | Symons Street | Junction with Sloane Square | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 23/06/25 | 01/08/25 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 82
Royal Borough of Kensington and Chelsea | Sloane Square | Junction with Holbein Place | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 02/07/25 | 21/07/25 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 83
Royal Borough of Kensington and Chelsea | Sloane Square | Junction with Sloane Street | Northbound Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 23/07/25 | 08/09/25 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 84
Royal Borough of Kensington and Chelsea | Sloane Square | Junction with Lower Sloane Street | Southbound Directional Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 15/09/25 | 2025-09-26 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 85
Royal Borough of Kensington and Chelsea | Sloane Square | Junction with Lower Sloane Street | Northbound Directional Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 2025-09-26 | 10/10/25 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Royal Hospital | 86
Royal Borough of Kensington and Chelsea | Gloucester Road | Stanhope Gardens to Cromwell Road | Northbound Directional Road Closure | 2025-10-01 | 2026-09-30 | Between 8.00am on first day until 6.00pm on final day. | Public Realm Scheme | Improvement Works | Courtfield | 87
Royal Borough of Kensington and Chelsea | Queens Gate Gardens | At it's junctions with Gloucester Road & Queens Gate Place | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | 2025-05-26 | 2025-08-18 | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Cycle Permeability | Queen's Gate | 88
Royal Borough of Kensington and Chelsea | Sidar Road | At it's junctions with Mary Place and Wilsham Street | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Notting Dale | 89
Royal Borough of Kensington and Chelsea | St Quintins Avenue | At it's junctions with Pangbourne Avenue & Wallingford Avenue | Road Closures/Carriageway width reduced/Footway width reduced/Parking Suspensions | TBC | TBC | Between 8.00am on first day until 6.00pm on final day. | Highway Improvement Works | Pedestrian Crossing Improvement Works | Dalgarno & St Helens | 90
|  |  |  | UTILITY COMPANY WORKS | [5 empty] | 91
Thames Water | Blenheim Crescent | Jnc Kensington Park Road | Road Closed with local diversion | 23-27/06/25 | Backup Dates 21-25/07/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 92
Compass Infrastructure for UKPN | Warwick Road | Fenlon Place to West Cromwell Road | Southbound Directional Road Closed with local diversion | 05-06/07/25 | Backup dates 12-13/07/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Abingdon | 93
Keltic Traffic Management for Cadent Gas | Ifield Road | Jnc Fulham Road | Road Closed with local diversion | 2025-07-06 | 2025-07-16 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Redcliffe | 94
OCU Group Limited | Allen Street | Northbound Directional Road Closure | Prohibited Right hand turns with local diversion | 07-12/07/25 | Backup Dates 14-19/07/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Abingdon | 95
Lanes Group for Thames Water | Hans Road | Brompton Road to Basil Street | Road Closed with local diversion | 2025-07-14 | 2025-07-16 | From 9.00mm until 5.00am Each Night | Utility works | Night Works | Brompton and Hans Town | 96
M Group for Thames Water | Talbot Road | 120, Powis Terrace to Powis Mews | Road Closed with local diversion | 20-21/07/25 | Backup Dates 27-28/07/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Colville | 97
M Group for Thames Water | Adderson Avenue | Holland Park Avenue | Cycle Lane Closed with local diversion | 2025-07-21 | 2025-08-03 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Norland | 98
Compass Infrastructure for UKPN | Notting Hill Gate | Jnc Clanricarde Gardens | Prohibited Right hand turns with local diversion | 21-25/07/25 | Backup Dates 22-26/07/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Pembridge | 99
M Group for Thames Water | Cale Street | 15 to jnc Whiteheads Grove | Road Closed with local diversion | 2025-07-28 | 2025-08-01 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Stanley | 100
Thames Water | King's Road | 21, Opp Peter Jones | Suspension of the Bus Lane | 28-30/07/25 | Backup Dates 04-06/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Royal Hospital | 101
M Group for Thames Water | Ladbroke Walk | O/s 10 | Road Closed with local diversion | 28/07/25 to 01/08/25 | Backup Dates 04-08/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Pembridge | 102
Thames Water | Old Brompton Road | Glendower Place towards the Station | Eastbound Directional Road Closed with local diversion | 2025-08-04 | 2025-08-11 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 103
M Group for Thames Water | Sydney Street | Fulham Road to outside 16 | Road Closed with local diversion | 04-13/08/25 | Backup Dates 15-24/09/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Stanley | 104
Cadent Gas | Onslow Gardens | 58 to 60 | Road Closed with local diversion | 04 -15/08/25 | Backup Dates 11-22/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Courtfield | 105
M Group for Thames Water | Kensington High Street | Jnc Campden Hill Road | Prohibited Right hand turns with local diversion | 11-20/08/25 | Backup Dates 18-28/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 106
M Group for Thames Water | Kyanace Mews | 10 | Road Closed with local diversion | 21-22/08/25 | Backup Dates 26-27/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 107
M Group for Thames Water | Kensington Church Court | R/o 82-84 Kensington High Street | Road Closed with local diversion | 04-08/08/25 | Backup Dates 11-15/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 108
M Group for Thames Water | Cavaye Place | Jnc 154 Fulham Road | Road Closed with local diversion | 05-07/08/25 | Backup Dates 02-04/09/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Redcliffe | 109
Compass Infrastructure for UKPN | Newcombe Street | Jnc Kensington Place | Road Closed with local diversion | 05-24/08/25 | Backup Dates 06-25/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 110
M Group for Thames Water | Ashburnham Road | 3 | Road Closed with local diversion | 11-14/08/25 | Backup Dates 18-21/08/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Chelsea Riverside | 111
Lanes Group PLC for Thames Water | Sloane Terrace | Jnc Sloane Street | Road Closed with local diversion | 2025-08-18 | 2025-08-19 | From 10.00pm until 5.30am | Utility works | Night Works | Brompton and Hans Town | 112
Kelly Traffic Management for Virgin Media | Yeoman's Row | Junction of Brompton Road | Road Closed with local diversion | 2025-08-23 | 2025-08-23 | From 8.00am until 6.00pm | Utility works |  | Brompton and Hans Town | 113
Thames Water | Earl's Court Road | Junction of Kensington High Street | Prohibited Right hand turn with local diversion | 26-28/08/25 | Backup dates 22-25/09/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Abingdon | 114
Cappagh for Thames Water | Draycott Avenue | Draycott Place | Road Closed with local diversion | 2025-08-28 | 2025-08-29 | From 9.00pm until 5.00am | Utility works | Night Works | Royal Hospital | 115
M Group for Thames Water | Whitehead's Grove | Sloane Avenue to Draycott Avenue | Road Closed with local diversion | 29/08/25 to 05/09/25 | Backup Dates 23-31/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 116
Kelly Traffic Management for Virgin Media | Pembridge Road | Portobello Road to Kensington Park Road | Southbound Directional Road Closed with local diversion | 29/08/25 to 05/09/25 | Backup Dates 23-31/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Pembridge | 117
Vital Energi | Dulford Street | Clarendon Road to Walmer Street | Road Closed with local diversion | 2025-09-04 | 2025-11-09 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Notting Dale | 118
Thames Water | Addison Avenue | Jnc Holland Park Avenue | Road Closed with local diversion | 08-21/09/25 | Backup Dates 07-21/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Norland | 119
M Group for Thames Water | Hollywood Road | O/s and Opp 55 | Road Closed with local diversion | 15-23/09/25 | Backup Dates 22-29/09/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Redcliffe | 120
M Group for Thames Water | Cale Street | Elystan Place to Elystan Street | Road Closed with local diversion | 15-23/09/25 | Backup Dates 22-29/09/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Stanley | 121
GTM for UKPN | Old Court Place | Jnc Kensington Church Street | Road Closed with local diversion | 15-26/09/25 | Backup Dates 22/09/25 to 03/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Campden | 122
Keltic Traffic Management for Cadent Gas | Tite Street | Chelsea Embankment to Dilke Street | Road Closed with local diversion | 2025-09-23 | 2025-09-23 | From 9.00am on first day until 4.00pm on final day | Utility works |  | Royal Hospital | 123
John Henry Group for Virgin Media | Hans Road | Basil Street to Hans Place | Southbound Directional Road Closed with local diversion | 2025-09-26 | Backup Date 03/10/25 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 124
Lanes Group PLC for Thames Water | Kenway Road | Whole Road | Road Closed with local diversion | 2025-10-27 | 2025-10-31 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Earl's Court | 125
M Group for Thames Water | Draycott Avenue | Brompton Road to Walton Street | Road Closed with local diversion | 23-27/02/26 | Backup Dates 02-06/03/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 126
M Group for Thames Water | Mossop Street | Ives Street to First Street | Road Closed with local diversion | 23-27/02/26 | Backup Dates 02-06/03/26 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Brompton and Hans Town | 127
|  |  |  | DEVELOPMENTS | [5 empty] | 128
Fenton Civils Limited | St Alban's Grove | 1 | Footway Closure | 05/05/25 to 28/07/25 | Backup dates 12/05/25 to 04/08/25 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Queen's Gate | 129
Knight Build Limited | Tryon Street | Whole Street | Development Works | 05/05/25 to 28/07/25 | Backup dates 12/05/25 to 04/08/25 | From 8.00am on first day until 6.00pm on final day | Developer works | S278 Works | Royal Hospital | 130
Neilcott Construction Ltd | Pelham Street | Brompton Road to Old Brompton Road | Westbourne Directional Road Closure | 2024-09-16 | 2026-02-09 | Weekdays From 8.00am on first day until 5.00pm on final day | Developer works |  | Brompton and Hans Town | 131
John F Hunt Limited | Hans Crescent | 2 to 4 | Footway Closure | 2024-10-03 | 2025-10-03 | From 8.00am on first day until 6.00pm on final day | Developer works |  | Brompton and Hans Town | 132
|  |  |  | MOBILE LIFTING OPERATIONS | [5 empty] | 133
City Lifting Limited | Pavilion Road | O/s 87 | Road closed with local diversion | 2025-07-08 | Backup Date 11/07/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 134
Size Group Limited | St John's Gardens | 1 | Road Width Reduced | 2025-07-08 | 2025-07-11 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 135
Mtec Fine Art limited | Cadogan Place | 25 | Road Width Reduced | 2025-07-14 | 2025-07-14 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 136
Lift Assist Limited | Portland Road | 37 | Road Width Reduced | 2025-07-16 | Backup date 23/07/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 137
GG 23 Limited | St Lukes Mews | Whole Road | Road closed with local diversion | 2025-07-16 | 2025-07-17 | From 8.00am on first day until 11.59pm on final day | Mobile Lifting Operation |  | Colville | 138
GG 23 Limited | All Saints Road | 7 | Road closed with local diversion | 2025-07-16 | 2025-07-17 | From 2.00pm on first day until 11.59pm on final day | Mobile Lifting Operation |  | Colville | 139
City Lifting Limited | Pelham Street | O/s 63 to 81 | Road closed with local diversion | 19-20/07/25 | Backup Dates 26-27/07/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 140
Size Group Limited | St John's Gardens | 1 | Road Width Reduced | 2025-07-21 | 2025-07-21 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 141
J & G Traffic Limited | St Lukes Mews | 29 | Road Width Reduced | 2025-07-21 | Backup date 27/07/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Colville | 142
National Lifting Solutions Limited | Hogarth Road | 15 to 25, Heaton Hotel | Road Width Reduced | 2025-07-22 | 2025-07-22 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Abingdon | 143
J & G Traffic Limited | Kelso Place | 45 to 46 | Road Width Reduced | 2025-07-24 | Backup date 30/07/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Queen's Gate | 144
Chevron Traffic Management | Exhibition Road | O/s The Victoria and Albert Museum | Road closed with local diversion | 2025-07-26 | Backup Date 02/08/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 145
Blade Traffic Management | King's Road | S/o Peter Jones | Suspension of the Bus Lane | 2025-07-27 | Backup Date 03/08/25 | From 8.00am to 4.00pm | Mobile Lifting Operation |  | Royal Hospital | 146
Lift Assist Limited | Lansdowne Road | 44 | Road Width Reduced | 2025-07-24 | Backup date 30/07/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Norland | 147
J & G Traffic Limited | Courtfield Gardens | 21 | Road Width Reduced | 2025-07-28 | Backup date 04/08/2025 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Courtfield | 148
Altman James Limited | Glebe Place | 36 | Road closed with local diversion | 2025-08-06 | Backup Date 07/08/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Chelsea Riverside | 149
R B F Limited | Philbeach Gardens | 63 to 47, O/s St Cuthbert's Church | Road closed with local diversion | 2025-08-06 | 2025-08-07 | From 8.00am to 8.00pm | Mobile Lifting Operation |  | Earl's Court | 150
Chevron Traffic Management | Exhibition Road | O/s The Victoria and Albert Museum | Road closed with local diversion | 2025-08-23 | Backup Date 30/08/25 | From 7.00am to 6.00pm | Mobile Lifting Operation |  | Brompton and Hans Town | 151
Chevron Traffic Management | Sloane Street | Whole Street | Road closed with local diversion | 2025-09-22 | 2025-09-23 | From 9.00pm until 6.00am | Mobile Lifting Operation | Night Works | Brompton and Hans Town | 152
Mechanical Movements and Enabling Services Limited | Wrights Lane | O/s Warner Music | Road closed with local diversion | 2025-10-11 | Backup Date 18/10/25 | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Queen's Gate | 153
Marjen Limited on behalf of Waldon Telecoms | Lancaster Road | Ladbroke Grove to 87 Lancaster Road | Road closed with local diversion | TBC | TBC | From 8.00am to 6.00pm | Mobile Lifting Operation |  | Colville | 154
|  |  |  | LOCAL RESIDENTS - STREET PARTIES & SPECIAL EVENTS | [5 empty] | 155
RBKC | Portobello Road | Colville Terrace to Oxford Gardens | Road Closed for a Street Market | 2025-06-22 | 2025-12-21 | Closed on Sundays From 8.00am until 5.00pm | Road Closed for a Street Market | Closed on Sundays | Colville and Golborne | 156
RBKC | Phillimore Walk | Hornton Street to Campden Hill Road | Road Closed for a Street Market | 2025-07-26 | 2025-07-26 | From 7.30am until 7.30pm | Road Closed for a Street Market |  | Campden | 157
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-08-08 | 2025-08-08 | Between 5.30pm and 10.00pm | Chelsea V Bayer 04 Leverkusen | Large amount of Pedestrians going to a football match | Various Wards | 158
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-08-10 | 2025-08-10 | Between 1.30pm and 6.00pm | Chelsea V AC Milan | Large amount of Pedestrians going to a football match | Various Wards | 159
Christchurch Residents Association | Christchurch Terrace | Christchurch Street to Havisham Street | Road Closed for a Community Event | 2025-08-17 | 2025-08-17 | Between 12.30pm and 6.30pm | Community Street party | VJ Day Celebration | Royal Hospital | 160
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-08-17 | 2025-08-17 | Between 12.30pm and 5.00pm | Chelsea V Crystal Palace | Large amount of Pedestrians going to a football match | Various Wards | 161
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-08-30 | 2025-08-30 | Between 12.30pm and 5.00pm | Chelsea V Fulham | Large amount of Pedestrians going to a football match | Various Wards | 162
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-09-27 | 2025-09-27 | Between 12.30pm and 5.00pm | Chelsea V Brighton & Hove Albion | Large amount of Pedestrians going to a football match | Various Wards | 163
RBKC - London Ambulance Charity Sponsored walk | Various Roads | Along the River Thames | Charity Walk | 2025-09-27 | 2025-09-27 | TBA | Charity Walk |  | Various Wards | 164
RBKC | Phillimore Walk | Hornton Street to Campden Hill Road | Road Closed for a Street Market | 2025-09-27 | 2025-09-27 | From 7.30am until 7.30pm | Road Closed for a Street Market |  | Campden | 165
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-10-04 | 2025-10-04 | Between 12.30pm and 5.00pm | Chelsea V Liverpool | Large amount of Pedestrians going to a football match | Various Wards | 166
King's Trust Palace to Palace | King's Road | Chelsea Embankment, Cheyne Walk, Cremorne Road, Ashburnham Road. | Large amount of cyclists on the Road | 2025-10-05 | 2025-10-05 | Between 7.00am until 10.30am | Charity Walk | Large amount of cyclists riding to Windsor | Chelsea Riverside | 167
RBKC | Phillimore Walk | Hornton Street to Campden Hill Road | Road Closed for a Street Market | 2025-10-25 | 2025-10-25 | From 7.30am until 7.30pm | Road Closed for a Street Market |  | Campden | 168
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-10-25 | 2025-10-25 | Between 12.30pm and 5.00pm | Chelsea V Sunderland | Large amount of Pedestrians going to a football match | Various Wards | 169
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-08 | 2025-11-08 | Between 12.30pm and 5.00pm | Chelsea V Wolverhampton Wanderers | Large amount of Pedestrians going to a football match | Various Wards | 170
RBKC | Phillimore Walk | Hornton Street to Campden Hill Road | Road Closed for a Street Market | 2025-11-29 | 2025-11-29 | From 7.30am until 7.30pm | Road Closed for a Street Market |  | Campden | 171
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-11-29 | 2025-11-29 | Between 12.30pm and 5.00pm | Chelsea V Arsenal | Large amount of Pedestrians going to a football match | Various Wards | 172
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-13 | 2025-12-13 | Between 12.30pm and 5.00pm | Chelsea V Everton | Large amount of Pedestrians going to a football match | Various Wards | 173
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-27 | 2025-12-27 | Between 12.30pm and 5.00pm | Chelsea V Aston Villa | Large amount of Pedestrians going to a football match | Various Wards | 174
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2025-12-30 | 2025-12-30 | Between 18.00pm and 11.00pm | Chelsea V Bournemouth | Large amount of Pedestrians going to a football match | Various Wards | 175
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-17 | 2026-01-17 | Between 12.30pm and 5.00pm | Chelsea V Brentford | Large amount of Pedestrians going to a football match | Various Wards | 176
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-01-31 | 2026-01-31 | Between 12.30pm and 5.00pm | Chelsea V West Ham United | Large amount of Pedestrians going to a football match | Various Wards | 177
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-02-11 | 2026-02-11 | Between 18.00pm and 11.00pm | Chelsea V Leeds United | Large amount of Pedestrians going to a football match | Various Wards | 178
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-02-21 | 2026-02-21 | Between 12.30pm and 5.00pm | Chelsea V Burnley | Large amount of Pedestrians going to a football match | Various Wards | 179
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-03-14 | 2026-03-14 | Between 12.30pm and 5.00pm | Chelsea V Newcastle United | Large amount of Pedestrians going to a football match | Various Wards | 180
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-04-11 | 2026-04-11 | Between 12.30pm and 5.00pm | Chelsea V Manchester City | Large amount of Pedestrians going to a football match | Various Wards | 181
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-04-18 | 2026-04-18 | Between 12.30pm and 5.00pm | Chelsea V Manchester United | Large amount of Pedestrians going to a football match | Various Wards | 182
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-02 | 2026-05-02 | Between 12.30pm and 5.00pm | Chelsea V Nottingham Forest | Large amount of Pedestrians going to a football match | Various Wards | 183
Chelsea Football Club | Fulham Road | Gunter Grove, Ifield Road, Hortensia Road, King's Road | Large amount of Pedestrians going to a football match | 2026-05-17 | 2026-05-17 | Between 12.30pm and 5.00pm | Chelsea V Tottenham Hotspur | Large amount of Pedestrians going to a football match | Various Wards | 184
|  |  |  | LOCAL ACTIVITIES ON THE TFL, HAMMERSMITH & FULHAM, WESTMINSTER OR BRENT NETWORKS | [5 empty] | 185
TfL | Battersea Bridge | North Side of the river | Lane and Junction restrictions | 2025-06-18 | 2025-10-03 | From 8.00am on first day until 6.00pm on final day | Junction improvement works |  | Chelsea Riverside | 186
TfL | Uxbridge Road and Shepherd's Bush Green | Around Holland Park Roundabout | Bus Lane Closures | 2025-06-30 | 2025-08-03 | From 7.30am on first day until 6.00pm on final day | Utility works | Buses are being diverted around Shepherd's Bush Green | LB Hammersmith and Fulham | 187
Cadent gas | North Pole Road | Scrubs Lane | Road Closed | 2025-07-06 | 2025-07-29 | From 8.00am on first day until 6.00pm on final day | Utility works | Major gas works at this junction | LB Hammersmith and Fulham | 188
UKPN | Brompton Road | 239-241 | F/w Closed Carriageway Walkway | 2025-07-07 | 2025-07-19 | From 8.00am on first day until 6.00pm on final day | Utility works |  | TfL | 189
UKPN | Warwick Road | 93 | Lane Closures | 2025-07-12 | 2025-07-13 | From 8.00am on first day until 12.00pm on final day | Utility works |  | Earl's Court | 190
UKPN | Warwick Road | Jnc Pennywern Road | Lane Closures | 2025-07-16 | 2025-07-16 | From 10.00am until 15.00pm | Utility works |  | Earl's Court | 191
Thames Water | Cromwell Road | Jnc Grenville Place | Offside lane closure | 2025-08-01 | 2025-08-02 | From 8.00am on first day until 6.00pm on final day | Utility works |  | Queen's Gate | 192
Thames Water | Eaton Gate | Eaton Square to Clivedon Place | Road Closed Local Diversions | 2025-08-04 | 2025-08-08 | From 0.00am on first day until 11.59pm on final day | Utility works |  | City of Westminster | 193
Thames Water | Eaton Gate | Eaton Square to Clivedon Place | Road Closed Local Diversions | 2025-11-13 | 2025-11-14 | From 0.00am on first day until 11.59pm on final day | Utility works |  | City of Westminster | 194
This list is not an exhaustive list of all works that are being carried out across the Borough.
For full details of all works being carried out in the borough please use the London Works facility using the following link:
http://one.network